## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone II to accommodate FHTC | SM/11658 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Dakshin Chatra Zone II Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002754/2021-2022 | 442/ BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.04 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone II to accommodate FHTC | SM/11658 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 1239/BD | 25/04/2023 | 25/04/2023 | Resource Division | 69.2 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone II to accommodate FHTC | SM/11658 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 1627/BD | 01/06/2023 | 01/06/2023 | Resource Division | 19.43 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone II to accommodate FHTC | SM/11658 | Augmentation | Formal work order for Laying of UPVC distribution pipeline and Providing FHTC (Functional Household Tap Connection) for Augmentation of Dakshin Chatra Zone-II Water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001186/2022-2023 | 1041/BD | 31/03/2023 | 12/05/2025 | DIAMOND ENGINEER'S CO-OP. SOCIETY LTD. | 378.49 | 0 | 0 | 37
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone II to accommodate FHTC | SM/11658 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No II (Rep.) (Zone-I and II) under Dakshin Chatra W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001911/2023-2024 | 6734/EMD | 29/11/2023 | 29/12/2023 | CONCORD ENGINEERING | 26.08 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone II to accommodate FHTC | SM/11658 | Augmentation | Dismantling of a dilapidated Room due to construction of Bio Eco Tech Plant at the Head Work site of Dakshin Chatra Zone I Water Supply Scheme under Barasat Division, P.H.E. | Assistant Engineer | Junior Engineer | ORD/000467/2024-2025 | 942/BHTSD | 24/05/2024 | 31/05/2024 | N.R. ENTERPRISE | 0.97 | 0 | 0 | 100
7 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone II to accommodate FHTC | SM/11658 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone II to accommodate FHTC | SM/11658 | Augmentation | Acceptance cum work order for Restoration of roads under different water supply schemes of Swarupnagar Block within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001009/2024-2025 | 3625/BD | 20/12/2024 | 20/03/2025 | PUSPA CONSTRUCTION. | 57.26 | 0 | 0 | 0
Total | [13 empty] | 21895.22 | 0 | 0