## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC | SM/11660 | Augmentation | Laying of pipe line at Dobila W/s scheme due to widening of PWD ROAD at Dobila Water supply scheme of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000463/2022-2023 | 837 /BHTSD | 23/06/2022 | 03/07/2022 | M/S SUKANTA ENTERPRISE. | 2.86 | 2.81 | 98.02 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC | SM/11660 | Augmentation | Sand filling due laying of pipe line at Dobila W/s scheme of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000505/2022-2023 | 845 /BHTSD | 23/06/2022 | 03/07/2022 | M/S SUKANTA ENTERPRISE. | 2.64 | 2.63 | 99.7 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC | SM/11660 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Dobila Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002756/2021-2022 | 449/ BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.5 | 3.5 | 100 | 1
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC | SM/11660 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Dobila W/S Scheme, Nabatkati W/S Scheme and Kurulia (Zone-II) W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001163/2023-2024 | 4813/EMD | 09/08/2023 | 08/09/2023 | DEBJYOTI BASU | 78.24 | 19.82 | 25.33 | 66
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC | SM/11660 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection) for Augmentation of Dobila Water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000232/2023-2024 | 1736/BD | 08/06/2023 | 29/11/2025 | M/S B.N ENTERPRISE | 223.65 | 161.46 | 72.19 | 36
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC | SM/11660 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 1273/BD | 25/04/2023 | 25/04/2023 | Resource Division | 94.49 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC | SM/11660 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000149/2023-2024 | 4407/BD | 10/11/2023 | 10/11/2023 | Resource Division | 5.73 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC | SM/11660 | Augmentation | Acceptance cum work order for Restoration of roads under different water supply schemes of Swarupnagar Block within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001009/2024-2025 | 3625/BD | 20/12/2024 | 20/03/2025 | PUSPA CONSTRUCTION. | 57.26 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC | SM/11660 | Augmentation | Regarding Restoration charges for road damages. |  |  | BILL/03464/2023-2024 | BP-2023-24-830 | 15/03/2024 | 15/03/2024 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 28.09 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC | SM/11660 | Augmentation | Acceptance cum work order for special repair and renovation of existing structure like Pump House, Boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Dobila, Eojnogar, Gobindapur Dhokra, Goknasree Gobindapur, Gotra, Sankchura and Mominpur Water Supply Scheme of different block within Basirhat Sub-Division under Barasat Division P.H.E. Dte. | Assistant Engineer |  | ORD/000287/2025-2026 | 2464/BD | 16/07/2025 | 13/12/2025 | M/S TARAFDAR CONSTRUCTION | 81.09 | 0 | 0 | 0
Total | [13 empty] | 577.57 | 190.22 | 32.93