## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durgapur Baylani Zone-II to accommodate FHTC. | SM/11664 | Augmentation | Acceptance cum Work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Durgapur Baylani w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000002/2023-2024 | 1097/BD | 06/04/2023 | 06/05/2023 | M/S RAJPATH CONSTRUCTION. | 21.46 | 16.98 | 79.09 | 0
2 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Durgapur Baylani Zone-II to accommodate FHTC. | SM/11664 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) and III(New) (Zone-II) under Durgapur-Baylani W/S Scheme with P/H-I, II and III(any 2 nos) under Kankpul W/S Scheme in District of 24 Pgs. (N) NIET No.- 32 of EE/EMD of 2022-23 (Sl. No.- 09) | Assistant Engineer | Junior Engineer | ORD/001971/2022-2023 | 1285/EMD | 28/03/2023 | 27/04/2023 | BENGAL CONSTRUCTION | 60.96 | 0 | 0 | 40
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durgapur Baylani Zone-II to accommodate FHTC. | SM/11664 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Durgapur Baylani water supply scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000947/2022-2023 | 89/BD | 11/01/2023 | 11/04/2023 | M/S DATTA ENTERPRISE. | 349.57 | 348.44 | 99.68 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durgapur Baylani Zone-II to accommodate FHTC. | SM/11664 | Augmentation | Formal work order for Construction of 300 cum capacity 20 mtr staging height R.C.C Over Head Reservoir as per Deptt. design, drawing & specification including bored pile with pile cap for Augmentation of Durgapur Baylani water supply scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001095/2023-2024 | 3021/BD | 05/10/2023 | 04/10/2024 | ABDUL ALIM MONDAL. | 122.76 | 33.87 | 27.59 | 100
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durgapur Baylani Zone-II to accommodate FHTC. | SM/11664 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000174/2022-2023 | 521/BD | 20/02/2023 |  | Resource Division | 138.01 | 0 | 0 | 0
Total | [13 empty] | 692.77 | 399.29 | 57.64