## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Maminpur to accommodate FHTC | SM/11665 | Augmentation | Route Survey, Design Drawing & DPR Preparation for MAMINPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002760/2021-2022 | 305/ BHTSD | 07/03/2022 | 22/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.15 | 2.98 | 94.72 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Maminpur to accommodate FHTC | SM/11665 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000145/2022-2023 | 3820/BD | 23/12/2022 | 23/12/2022 | Resource Division | 16.81 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Maminpur to accommodate FHTC | SM/11665 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method for pump house no - 1 & 2 using PVC pipe & strainer having 300 mm Dia 36 mtr. long Housing Pipe and 200 mm Dia 30 mtr. long filter for Augmentation of Mominpur Water Supply Scheme in Basirhat - II Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001151/2022-2023 | 674/BD | 01/03/2023 | 31/03/2023 | DHELA BABA ENTERPRISE | 42.67 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Maminpur to accommodate FHTC | SM/11665 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000157/2023-2024 | 4417/BD | 10/11/2023 | 10/11/2023 | Resource Division | 11.09 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Maminpur to accommodate FHTC | SM/11665 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Bansjhari-Mullickpur and Maminpur W/S Scheme with Pump House No-I under Rajnagar W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/003332/2023-2024 | 4809./EMD | 09/08/2023 | 08/09/2023 | S.G. ENTERPRISE | 65.16 | 14.79 | 22.69 | 75
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Maminpur to accommodate FHTC | SM/11665 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Maminpur water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000742/2022-2023 | 3340/BD | 16/11/2022 | 24/12/2024 | MONDAL PRECISION PVT.LTD | 194.77 | 155.27 | 79.72 | 83
Total | [13 empty] | 333.65 | 173.04 | 51.86