## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC | SM/11666 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Ghatpatila (Zone-II) Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002779/2021-2022 | 131/Bon | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.89 | 3.89 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC | SM/11666 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000156/2022-2023 | 1257/BD | 25/04/2023 | 25/04/2023 | Resource Division | 64.8 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC | SM/11666 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000093/2023-2024 | 1861/BD | 23/06/2023 | 23/06/2023 | Resource Division | 15.65 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC | SM/11666 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for augmentation of Ghatpatila (Zone-II) Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000036/2023-2024 | 1354/BD | 04/05/2023 | 20/10/2025 | PATHIK PABAN NANDI | 403.71 | 370.5 | 91.77 | 95
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC | SM/11666 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Zone-II) (Replacement) under Ghatpatila W/S Scheme District of 24 Pgs. (N). | Assistant Engineer | Junior Engineer | ORD/001893/2023-2024 | 6755/EMD | 28/11/2023 | 28/12/2023 | GOENKA ENTERPRISE | 22.16 | 7.28 | 32.88 | 80
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC | SM/11666 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Ghatpatila (Zone-II) water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000767/2023-2024 | 2688/BD | 04/09/2023 | 04/10/2023 | B.M.ENGINEERING. & CONSTRUCTION. | 16.13 | 13.46 | 83.47 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC | SM/11666 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Ghatpatila (Zone-II) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001457/2023-2024 | 4409/BD | 10/11/2023 | 09/01/2024 | ROY CHOWDHURY CONSTRUCTION. | 15.27 | 15.23 | 99.7 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC | SM/11666 | Augmentation | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Ghatpatila (Zone-II) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001488/2023-2024 | 4463/BD | 21/11/2023 | 08/01/2025 | ROY ENGINEERS. | 9.57 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC | SM/11666 | Augmentation | Formal work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe line under Augmentation work at Ghatpatila (Zone - II) W/S Scheme Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001051/2024-2025 | 3736/BD | 27/12/2024 | 22/03/2026 | PATHIK PABAN NANDI | 120.24 | 0 | 0 | 80
10 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC | SM/11666 | Augmentation | Repairing of outdoor light and allied work at P.H. no.l , Zone -II of Ghatpatila WS Scheme under EMSD-l, P.H.E. Dte. Dist.-24Pgs(N). | Assistant Engineer | Junior Engineer | ORD/000014/2025-2026 | 451/EMSD-I | 08/04/2025 | 08/05/2025 | M/S.A.K. BANERJEE. | 4.17 | 0 | 0 | 100
11 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC | SM/11666 | Augmentation | Quotation for 10 KWp Solar power plant at P.H.No- I , Zone - II of Ghatpatila ground water based water supply scheme under EMSD-I ,PHE Dte. in Dist.- 24Pgs(N). |  |  | BILL/03024/2025-2026 |  | 07/01/2026 | 07/01/2026 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.15 | 0 | 0 | 0
Total | [13 empty] | 675.75 | 410.37 | 60.73