## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | SM/11667 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Matiagacha W/S Scheme in Habra - II Block under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002763/2021-2022 | 128/HAB | 16/03/2022 | 26/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.35 | 3.27 | 97.43 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | SM/11667 | Augmentation | Repairing & Renovation of 01No. Pump House and allied works at Matiagacha water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002937/2021-2022 | 530/BON | 03/11/2021 | 24/11/2021 | KAMAL HALDER. | 2.52 | 2.5 | 99.18 | 1
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | SM/11667 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. II under Matigacha (Block:-Barasat-II) W/S Scheme District of 24 Pgs. (N) N.I.E.T No. 27 of EE / EMD of 2022-2023 (2022_PHED_431015_28) |  |  | ORD/001888/2023-2024 | 6731/EMD | 28/11/2023 | 28/12/2023 | M.D. ENTERPRISE | 10.69 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | SM/11667 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 1252/BD | 25/04/2023 | 25/04/2023 | Resource Division | 8.28 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | SM/11667 | Augmentation | Acceptance cum work order for Repairing of Boundary wall and Construction of Approach Road at Head Work site & 2nd Pump House site under Augmentation of Matiagachha Water Supply Scheme, Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001746/2023-2024 | 563/BD | 22/02/2024 | 07/04/2024 | M/S SANDHYA CONSTRUCTION | 9.88 | 9.87 | 99.86 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | SM/11667 | Augmentation | Acceptance cum work order for Repairing and renovation works of 200 cum. capacity 20mtr. Staging height R.C.C. Over Head water Reservoir for Augmentation of Matiagachha Water Supply Scheme, Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000010/2024-2025 | 1535/BD | 07/06/2024 | 22/07/2024 | B.S.ENTERPRISE. (BASIRHAT) | 13.15 | 13.11 | 99.68 | 100
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | SM/11667 | Augmentation | Payment of invoice bill for new service connection at PH-III under Matiagacha W/S Scheme. |  |  | BILL/04811/2023-2024 | BP-303-23-24 | 04/03/2024 | 04/03/2024 | W.B.S.E.D.C.L. (GANGANAGAR C.C.C.) | 3.94 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | SM/11667 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II Matiagacha (Block-Habra II) W/S Scheme and Pump House No.I & II Ashudi W/S scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001915/2023-2024 | 6738/EMD | 29/11/2023 | 01/06/2025 | M/S S.R. ENTERPRISE | 42.55 | 0 | 0 | 50
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | SM/11667 | Augmentation | Formal work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe under Augmentation work at Matiagachha W/S Scheme at Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. (SM/11667) | Assistant Engineer | Junior Engineer | ORD/000643/2024-2025 | 3130/BD | 12/11/2024 | 11/05/2025 | M/S SUKANTA ENTERPRISE. | 115.81 | 0 | 0 | 30
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | SM/11667 | Augmentation | Formal work order fior Laying of DI rising main, UPVC distribution pipe line and Providing Functional Household Tap Connection for augmentation of Matiagacha Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000033/2023-2024 | 1356/BD | 04/05/2023 | 23/04/2025 | M/S R.K. ENTERPRISE | 231.73 | 130.41 | 56.28 | 80
Total | [13 empty] | 441.89 | 159.15 | 36.01