## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Chaital to accommodate FHTC | SM/11669 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000259/2022-2023 | 921/BD | 22/03/2023 | 22/03/2023 | Resource Division | 101.89 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Chaital to accommodate FHTC | SM/11669 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Replacement) under Bharatpur W/S Scheme, Patua W/S Scheme (P/H-I & II) & Chaital W/S Scheme (P/H -I & II) District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 04) | Assistant Engineer | Junior Engineer | ORD/000824/2022-2023 | 31/EMD | 03/01/2023 | 01/04/2025 | M/S P.P. ELECTRICALS | 74.67 | 13.02 | 17.43 | 73
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Chaital to accommodate FHTC | SM/11669 | Augmentation | Formal work order for Additional Laying of DI/UPVC distribution pipe line and Providing Functional Household Tap Connection for the leftout portion in connection with Augmentation of Chaital water supply scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002054/2023-2024 | 881/BD | 14/03/2024 | 12/06/2024 | M/S B.K.ENTERPRISE. | 140.08 | 63.01 | 44.98 | 80
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Chaital to accommodate FHTC | SM/11669 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Chaital water supply scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001135/2022-2023 | 517/BD | 20/02/2023 | 21/05/2023 | M/S B.K.ENTERPRISE. | 372.13 | 351.13 | 94.36 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Chaital to accommodate FHTC | SM/11669 | Augmentation | Formal work order for construction of 500 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Chaital water supply scheme, Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000792/2023-2024 | 2614/BD | 29/08/2023 | 28/08/2024 | M/S B.K.ENTERPRISE. | 203.43 | 120.47 | 59.22 | 75
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Chaital to accommodate FHTC | SM/11669 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection with augmentation of Chaital water supply scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001398/2024-2025 | 264/HSD | 30/01/2025 | 09/02/2025 | M/S R.B.S.ENTERPRISE. | 0.62 | 0 | 0 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Chaital to accommodate FHTC | SM/11669 | Augmentation | Acceptance cum work order for Sand filling at ditch area for construction of temporary approach road for movement of winch machine and other allied machineries at OHR site within Chaital W/S scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001449/2024-2025 | 324/HSD | 04/02/2025 | 14/02/2025 | M/S R.B.S.ENTERPRISE. | 0.95 | 0 | 0 | 100
Total | [13 empty] | 893.78 | 547.63 | 61.27