## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC | SM/11699 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000090/2022-2023 | 3421/BD | 23/11/2022 | 23/11/2022 | Resource Division | 62.56 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC | SM/11699 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Khulna Bhanderkhali W/S scheme (Zone-II), Sandeshkhali-II Block within Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000663/2022-2023 | 2722/BD | 14/09/2022 | 13/12/2022 | S.S.ENTERPRISE. (BAMANGACHI) | 345.34 | 320.2 | 92.72 | 1
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC | SM/11699 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Zone-II) (Replacement) under Kulna-Bhanderkhali W/S Scheme District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 09) | Assistant Engineer | Junior Engineer | ORD/000831/2022-2023 | 36/EMD | 03/01/2023 | 02/02/2023 | JAL PRAVAHIKA PVT. LTD. | 26.49 | 24.17 | 91.25 | 100
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC | SM/11699 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.III (Zone-II) (Replacement) under Khulna-Bhanderkhali W/S Scheme District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 10) | Assistant Engineer | Junior Engineer | ORD/000832/2022-2023 | 37/EMD | 03/01/2023 | 02/02/2023 | D.K. ELECTRIC | 13.24 | 12.36 | 93.33 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC | SM/11699 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Khulna Bhanderkhali w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001172/2022-2023 | 785/BD | 13/03/2023 | 12/04/2023 | M/S NIRMAN CONSTRUCTION. | 47.08 | 36.84 | 78.23 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC | SM/11699 | Augmentation | Acceptance cum work order for Construction of boundary wall at pond site for damaged portion & repairing of existing boundary wall at CWR site within Khulna Bhanderkhali w/s scheme (Zone-II), Sandeshkhali-II Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000298/2023-2024 | 2113/BD | 19/07/2023 | 09/08/2023 | ANKUSH CONSTRUCTION & CO. | 6.14 | 6.14 | 100 | 55
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC | SM/11699 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Khulna Bhanderkhali w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000737/2023-2024 | 2491/BD | 18/08/2023 | 17/09/2023 | M/S PROGATI ENTERPRISE. | 26.89 | 20.57 | 76.49 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC | SM/11699 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000255/2022-2023 | 941/BD | 22/03/2023 | 22/03/2023 | Resource Division | 9.14 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC | SM/11699 | Augmentation | Acceptance cum work order for Protection works in different places for protection of different dia DI/UPVC rising/distribution pipe line by UC bullah/Bamboo pile for Augmentation of Khulna Bhandarkhali Zone-II w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/000848/2023-2024 | 2656/BD | 01/09/2023 | 01/10/2023 | M/S DATTA ENTERPRISE. | 58.87 | 58.07 | 98.65 | 85
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC | SM/11699 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Khulna Bhanderkhali water supply scheme (Z-II) , Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001297/2023-2024 | 1419/HSD | 06/11/2023 | 13/11/2023 | DEB PRASAD GHOSH. | 0.96 | 0.96 | 99.7 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC | SM/11699 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-3 in connection with Augmentation for Khulna Bhanderkhali water supply scheme (Z-II) , Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001296/2023-2024 | 1418/HSD | 06/11/2023 | 13/11/2023 | DEB PRASAD GHOSH. | 0.93 | 0.93 | 100 | 100
12 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC | SM/11699 | Augmentation | Quotation for Service Connection Charges for PH- III under Bhanderkhali W/S Scheme in the district of North 24 Pgs. JL No. 92, Plot No-112. |  |  | BILL/04886/2023-2024 | BP-321-23-24 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.02 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC | SM/11699 | Augmentation | Quotation for Service Connection Charges for PH- I under Bhanderkhali W/S Scheme in the district of North 24 Pgs. JL No- 92, Plot No-1 & 65/264 |  |  | BILL/04885/2023-2024 |  | 04/03/2024 | 04/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.55 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC | SM/11699 | Augmentation | Formal work order for Construction of 150 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Khulna Bhanderkhali (Zone-II) under Surface Based Water Supply Scheme Hasnabad under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000321/2024-2025 | 2261/BD | 12/08/2024 | 12/08/2025 | B.S.ENTERPRISE. (BASIRHAT) | 115.79 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC | SM/11699 | Augmentation | Acceptance cum work order for Providing Functional tap connection at Sitalia Khaitala SSK, ICDS Centre no-77, Dakshin Sitalia FP School, South Hatgacha Jr. Basic School and Hatgacha Goramari FP Schoolwithin the command area of Khulna Bhanderkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. |  |  | ORD/000148/2025-2026 | 997/HSD | 04/06/2025 | 14/06/2025 | RAJPATH ENGINEERS-CO-OPERATIVE SOCIETY LTD. | 0.96 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC | SM/11699 | Augmentation | Acceptance cum work order for Repairing of Pump House at PH No- 1, 2 & 3 in connection with augmentation of Khulna Bhandarkhali w/s scheme (Zone-II), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001711/2024-2025 | 895/BD | 20/03/2025 | 03/06/2025 | GAZI ENTERPRISE | 5.52 | 0 | 0 | 0
Total | [13 empty] | 734.49 | 480.24 | 65.38