## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Arsula to accommodate FHTC | SM/11700 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 1237/BD | 25/04/2023 | 25/04/2023 | Resource Division | 141.41 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Arsula to accommodate FHTC | SM/11700 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000139/2023-2024 | 4425/BD | 10/11/2023 | 10/11/2023 | Resource Division | 17.4 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Arsula to accommodate FHTC | SM/11700 | Augmentation | Regarding Restoration charges for road damages. |  |  | BILL/03460/2023-2024 | BP-2023-24-830 | 15/03/2024 | 15/03/2024 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 18.45 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Arsula to accommodate FHTC | SM/11700 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Arsula water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000024/2023-2024 | 1217/BD | 20/04/2023 | 27/08/2025 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 667.97 | 389.66 | 58.33 | 55
5 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Arsula to accommodate FHTC | SM/11700 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 22.94 | 0.11 | 11
6 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Arsula to accommodate FHTC | SM/11700 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Rep.) and IV (New) under Gokna W/S Scheme and Pump House No- II (Rep) under Arsula W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001912/2023-2024 | 6735/EMD | 29/11/2023 | 01/04/2025 | M.S. ENTERPRISE | 39.12 | 0 | 0 | 30
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Arsula to accommodate FHTC | SM/11700 | Augmentation | Acceptance cum work order for Restoration of roads under different water supply schemes of Baduria Block within Basirhat Sub-Division under Barasat Division P.H.E.Dte | Assistant Engineer | Junior Engineer | ORD/001008/2024-2025 | 3553/BD | 16/12/2024 | 10/01/2026 | PRITAM MUKHOPADHYAY. | 60.15 | 0 | 0 | 0
Total | [13 empty] | 22284.25 | 412.6 | 1.85