## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-II to accommodate FHTC | SM/11701 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Bajitpur Zone-II water supply scheme (Zone-II), in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000012/2023-2024 | 1190/BD | 19/04/2023 | 18/07/2023 | DIVINE | 330.08 | 279.28 | 84.61 | 50
2 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-II to accommodate FHTC | SM/11701 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) with Pump House no-III(New) under Monipur W/S Scheme with Bajitpur (I and II, Zone-II) W/S Scheme in District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001916/2023-2024 | 6739/EMD | 29/11/2023 | 29/12/2023 | GLACIER ENGINEERING CO. | 67.8 | 0 | 0 | 40
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-II to accommodate FHTC | SM/11701 | Augmentation | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Bazitpur, zone - II W/S Scheme including increasing the height of back wash water tank at Baduria Block under Basirhat Sub Division, PHE Dte. Capacity- 90.00 Cum/hr. | Assistant Engineer | Junior Engineer | ORD/002035/2023-2024 | 921/BD | 15/03/2024 | 14/05/2024 | MONDAL PRECISION PVT.LTD | 36.2 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-II to accommodate FHTC | SM/11701 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2023-2024 | 1236/BD | 25/04/2023 |  | Resource Division | 4.59 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-II to accommodate FHTC | SM/11701 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 1633/BD | 01/06/2023 |  | Resource Division | 10.1 | 0 | 0 | 0
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-II to accommodate FHTC | SM/11701 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 1646/BD | 02/06/2023 |  | Resource Division | 13.76 | 0 | 0 | 0
Total | [13 empty] | 462.53 | 279.28 | 60.38