## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mirjanagar to accommodate FHTC | SM/11702 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000185/2022-2023 | 606/BD | 23/02/2023 | 23/02/2023 | Resource Division | 10.48 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mirjanagar to accommodate FHTC | SM/11702 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000200/2022-2023 | 856/BD | 20/03/2023 | 20/03/2023 | Resource Division | 23.33 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mirjanagar to accommodate FHTC | SM/11702 | Augmentation | Acceptance cum work order for Restoration of roads under different water supply schemes of Basirhat II Block within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer |  | ORD/001010/2024-2025 | 3554/BD | 16/12/2024 | 15/01/2025 | M/S MAA TARA ENTERPRISE | 29.52 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mirjanagar to accommodate FHTC | SM/11702 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipeline and Providing FHTC (Functional Household Tap Connection ) for augmentation of Mirjanagar water supply scheme in Basirhat-II block of North 24 Parganas District under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 3476/BD | 01/12/2022 | 01/03/2023 | SUPER SKILL. | 288.66 | 287.73 | 99.68 | 90
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mirjanagar to accommodate FHTC | SM/11702 | Augmentation | Acceptance cum work order for Special repair and renovation of existing structures like Pump House, Boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Itinda Panitor, Joypur Gopmahal, Kachua Swarupnagar, Mathurapur, Mirzanagar, Nalkora, Paikardanga, Pifa and Gobindapur Water Supply Scheme of different block under Basirhat Sub-Division within Barasat Division, P.H.E Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 2474/BD | 17/07/2025 | 14/12/2025 | SAHA CONSTRUCTION & CO | 91.3 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mirjanagar to accommodate FHTC | SM/11702 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method at Pump House 2 using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Mirjanagar Water Supply Scheme in Basirhat - II Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000771/2024-2025 | 3259/BD | 25/11/2024 | 11/04/2025 | ANJALI ENTERPRISE. | 21.75 | 0 | 0 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mirjanagar to accommodate FHTC | SM/11702 | Augmentation | Acceptance cum work order for Restoration of roads and emergency protection work under different places of Mirzanagar Water Supply Scheme within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002175/2024-2025 | 1021/BD | 28/03/2025 | 27/05/2025 | LUCKY CONSTRUCTION. | 5.69 | 0 | 0 | 100
Total | [13 empty] | 470.73 | 287.73 | 61.12