## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Debipur to accommodate FHTC | SM/11703 | Augmentation | Construction of pathway & Land development at H/W site of Dakshin Debipur Water Supply Scheme under Basirhat-Il Block under Basirhat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001929/2021-2022 | 380/BHTSD | 17/03/2022 | 06/04/2022 | M/S MITRA CONSTRUCTION. | 3.27 | 3.17 | 97.13 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Debipur to accommodate FHTC | SM/11703 | Augmentation | Route Survey, Design Drawing & DPR Preparation for DAKSHIN DEBIPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002794/2021-2022 | 312/ BHTSD | 07/03/2022 | 22/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.87 | 2.87 | 100 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Debipur to accommodate FHTC | SM/11703 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000146/2022-2023 | 3815/BD | 23/12/2022 | 23/12/2022 | Resource Division | 2.38 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Debipur to accommodate FHTC | SM/11703 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Dakshin Debipur water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000748/2022-2023 | 3373/BD | 18/11/2022 | 16/02/2023 | CHANCHAL ENTERPRISE & CO. | 212.57 | 212.53 | 99.98 | 85
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Debipur to accommodate FHTC | SM/11703 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2022-2023 | 2306/BD | 03/08/2022 | 03/08/2022 | Resource Division | 2.3 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dakshin Debipur to accommodate FHTC | SM/11703 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Replacement) under Dakshin Debipur W/S Scheme District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer | ORD/000827/2022-2023 | 33/EMD | 03/01/2023 | 02/02/2023 | JAL PRAVAHIKA PVT. LTD. | 26.07 | 0 | 0 | 60
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Debipur to accommodate FHTC | SM/11703 | Augmentation | Acceptance cum work order for Providing new FHTC (Functional Household Tap Connection) by Augmentation and relaying of rising main, distribution UPVC pipe line and repairing of existing FHTC connection which damaged due to construction of drain by local Panchayet from Pump house I to Pump house II of Dakshin Debipur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000800/2024-2025 | 3294/BD | 26/11/2024 | 24/06/2025 | ROHAN MONDAL. | 57.65 | 0 | 0 | 80
Total | [13 empty] | 307.1 | 218.56 | 71.17