## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bara Bankra to accommodate FHTC | SM/11704 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 1271/BD | 25/04/2023 | 25/04/2023 | Resource Division | 149.36 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bara Bankra to accommodate FHTC | SM/11704 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Baro Bankra water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000164/2023-2024 | 1720/BD | 08/06/2023 | 11/03/2025 | MADE & TRADE CO. | 433.09 | 343.7 | 79.36 | 58
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bara Bankra to accommodate FHTC | SM/11704 | Augmentation | Regarding Restoration charges for road damages. |  |  | BILL/03462/2023-2024 | BP-2023-24-830 | 15/03/2024 | 15/03/2024 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 31.71 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Bara Bankra to accommodate FHTC | SM/11704 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II, III and IV (Rep.) under Nalabara W/S Scheme and Pump House No-I and II under Barabankra W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001161/2023-2024 | 4811/EMD | 09/08/2023 | 01/06/2025 | M/S. SAJAHAN CHOWDHURY | 78.21 | 3.67 | 4.69 | 46
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bara Bankra to accommodate FHTC | SM/11704 | Augmentation | Acceptance cum work order for special repair renovation of existing structures like Pump house, Boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Akhipur, Baro Bankra, Bithari Z-I, Bithari Z-II water supply scheme of different block under Basirhat Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000265/2025-2026 | 2381/BD | 10/07/2025 | 07/12/2025 | JP CONSTRUCTION & SUPPLIERS. | 81.91 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bara Bankra to accommodate FHTC | SM/11704 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method at pump house 1 using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Boro Bankra Water Supply Scheme in Swarupnagar Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000773/2024-2025 | 3265/BD | 25/11/2024 | 25/03/2025 | JOY GURU ENTERPRISE | 21.74 | 0 | 0 | 100
Total | [13 empty] | 796.02 | 347.37 | 43.64