## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Debhog to accommodate FHTC | SM/11753 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 1250/BD | 25/04/2023 | 25/04/2023 | Resource Division | 17.73 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Debhog to accommodate FHTC | SM/11753 | Augmentation | Formal work order for Laying of UPVC Distribution system pipe line and Providing FHTC (Functional Household Tap Connection ) by augmentation for Debhog water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001137/2022-2023 | 518/BD | 20/02/2023 | 03/04/2025 | UTPAL CONSTRUCTION & CO. | 301.59 | 0 | 0 | 80
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Debhog to accommodate FHTC | SM/11753 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Debhog Water Supply Scheme in Basirhat - I Block of Basirhat Sub- Division under Barasat Division, P.H.E Dte. | Assistant Engineer |  | ORD/000704/2024-2025 | 3254/BD | 25/11/2024 | 25/12/2024 | ROHAN MONDAL. | 21.41 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Debhog to accommodate FHTC | SM/11753 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Debhog to accommodate FHTC | SM/11753 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Sankarpur and P/H-II under Debhog W/S Scheme with Pump House No-I under Gachharhati W/S Scheme District of 24 Pgs. (N). | Assistant Engineer | Junior Engineer | ORD/000026/2024-2025 | 1483/EMD | 03/06/2024 | 28/03/2025 | EASTERN INDIA SALES & SERVICE | 52.16 | 0 | 0 | 25
Total | [13 empty] | 21732.66 | 0 | 0