## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bagundi to accommodate FHTC | SM/11754 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000143/2022-2023 | 3814/BD | 23/12/2022 | 23/12/2022 | Resource Division | 17.36 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bagundi to accommodate FHTC | SM/11754 | Augmentation | Acceptance cum work order for Laying of UPVC distribution main and Providing FHTC (Functional Household Tap Connection ) by augmentation for Dakshin Bagundi water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000785/2022-2023 | 3511/BD | 02/12/2022 | 01/01/2023 | ROY CHOWDHURY CONSTRUCTION. | 50.96 | 43.28 | 84.92 | 85
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bagundi to accommodate FHTC | SM/11754 | Augmentation | Acceptance cum work order for Construction of Boundary Wall at the site of Pump House 1 of Dakshin Bagundi Water Supply Scheme under Basirhat Sub-Division within Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001038/2024-2025 | 3701/BD | 26/12/2024 | 22/09/2025 | JEET ENTERPRISE. | 7.96 | 0 | 0 | 0
Total | [13 empty] | 76.28 | 43.28 | 56.73