## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kulia to accommodate FHTC | SM/11755 | Augmentation | Acceptance cum work order for Laying of UPVC distribution main and Providing FHTC (Functional Household Tap Connection ) by augmentation for Kulia water supply scheme in Baduria block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000813/2022-2023 | 3586/BD | 08/12/2022 | 07/01/2023 | PREMANANDA ROY BISWAS. | 73.89 | 72.44 | 98.04 | 100
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kulia to accommodate FHTC | SM/11755 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000161/2022-2023 | 494/BD | 17/02/2023 | 17/02/2023 | Resource Division | 2.75 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Kulia to accommodate FHTC | SM/11755 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21416.4 | 72.44 | 0.34