## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Taranipur Zone I to accommodate FHTC | SM/11757 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Taranipur Zone I Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002758/2021-2022 | 446/ BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.69 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Taranipur Zone I to accommodate FHTC | SM/11757 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2023-2024 | 1272/BD | 25/04/2023 | 25/04/2023 | Resource Division | 5.86 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Taranipur Zone I to accommodate FHTC | SM/11757 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection) for Augmentation of Taranipur Zone-I Water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000235/2023-2024 | 1734/BD | 08/06/2023 | 27/02/2025 | DIVINE | 307.75 | 0 | 0 | 75
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Taranipur Zone I to accommodate FHTC | SM/11757 | Augmentation | Shifting of One DTR DP structure includuing 63 KVA DTR and one T-Off 9 mtr PCC Pole to the adjucent location on request. |  |  | BILL/02016/2024-2025 | BP-166-24-25 | 25/11/2024 | 25/11/2024 | W.B.S.E.D.C.L (TEHATTA CCC) | 0.93 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Taranipur Zone I to accommodate FHTC | SM/11757 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II, III and IV (Rep.) under Bithari (Zone-I) W/S Scheme and Pump House No-I under Taranipur (Zone-I) W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001889/2023-2024 | 6752/EMD | 28/11/2023 | 01/04/2025 | M.S. ENTERPRISE | 65.12 | 0 | 0 | 60
6 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Taranipur Zone I to accommodate FHTC | SM/11757 | Augmentation | Providing outdoor illumination arrangement at P.H. No.- I, Zone-I under Taranipur W/S Scheme under EMSD-I, P.H.E. Dte. Dist.- 24PGS(N). | Assistant Engineer | Junior Engineer | ORD/000018/2025-2026 | 455/EMSD-I | 08/04/2025 | 03/05/2025 | AMIT DAS | 1.36 | 0 | 0 | 0
Total | [13 empty] | 384.7 | 0 | 0