## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sonpur to accommodate FHTC | SM/11758 | Augmentation | Route Survey, Design Drawing & DPR Preparation for SONPUR Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002497/2021-2022 | 458 / BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.87 | 2.87 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sonpur to accommodate FHTC | SM/11758 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000148/2022-2023 | 3809/BD | 23/12/2022 | 23/12/2022 | Resource Division | 0.41 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sonpur to accommodate FHTC | SM/11758 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Sonpur water supply scheme in Swarupnagar block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000750/2022-2023 | 3401/BD | 21/11/2022 | 19/02/2023 | M/S ANUBHAB CONSTRUCTION. | 133.98 | 127.7 | 95.31 | 95
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sonpur to accommodate FHTC | SM/11758 | Augmentation | Providing voltage correction arrangement with allied works at PH-I of Sonpur GRW W/S Scheme under EMSD-I. |  |  | ORD/001695/2023-2024 | 1780EMSD-I | 10/08/2023 | 09/09/2023 | P.K. ENTERPRISE | 3.15 | 3.12 | 99.28 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sonpur to accommodate FHTC | SM/11758 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000152/2023-2024 | 4413/BD | 10/11/2023 | 10/11/2023 | Resource Division | 6.16 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sonpur to accommodate FHTC | SM/11758 | Augmentation | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Sonepur W/S Scheme including increasing the height of back wash water tank at Swarupnagara Block under Basirhat Sub Division, PHE Dte. Capacity-10.00Cum/hr. | Assistant Engineer | Junior Engineer | ORD/002033/2023-2024 | 924/BD | 15/03/2024 | 10/03/2025 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 23.32 | 0 | 0 | 75
Total | [13 empty] | 169.89 | 133.69 | 78.69