## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nabatkati to accommodate FHTC | SM/11760 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Nabatkati Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002753/2021-2022 | 459/ BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.81 | 3.81 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nabatkati to accommodate FHTC | SM/11760 | Augmentation | Formal work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Nabatkati Water Supply Scheme at Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000005/2022-2023 | 1135/BD | 12/04/2022 | 11/07/2022 | UTPAL CONSTRUCTION & CO. | 184.62 | 36.58 | 19.81 | 12
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nabatkati to accommodate FHTC | SM/11760 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000202/2022-2023 | 858/BD | 20/03/2023 | 20/03/2023 | Resource Division | 0.84 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nabatkati to accommodate FHTC | SM/11760 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Nabatkati water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001140/2022-2023 | 513/BD | 20/02/2023 | 24/05/2025 | UTPAL CONSTRUCTION & CO. | 285.35 | 208.83 | 73.18 | 60
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Nabatkati to accommodate FHTC | SM/11760 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Dobila W/S Scheme, Nabatkati W/S Scheme and Kurulia (Zone-II) W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001163/2023-2024 | 4813/EMD | 09/08/2023 | 08/09/2023 | DEBJYOTI BASU | 78.24 | 15.54 | 19.86 | 66
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nabatkati to accommodate FHTC | SM/11760 | Augmentation | Relaying of 75mm dia UPVC pipe line and repairing of FHTC connections due to damaged during construction of road by WBSRDA at Node no. 100 to 175 of Nabatkati water Supply Scheme under Basirhat Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000445/2024-2025 | 1169/BHTSD | 30/07/2024 | 14/08/2024 | M/S. WAY CON. | 0.88 | 0.88 | 99.74 | 50
Total | [13 empty] | 553.75 | 265.64 | 47.97