## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC | SM/11761 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 1240/BD | 25/04/2023 | 25/04/2023 | Resource Division | 13.72 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC | SM/11761 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Gadpukuria (Zone-I) Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001152/2023-2024 | 2926/BD | 26/09/2023 | 26/10/2023 | B.M.ENGINEERING. & CONSTRUCTION. | 16.12 | 13.81 | 85.69 | 100
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC | SM/11761 | Augmentation | Acceptance cum work order for Renovation of 103 Cum/hr of capacity AIRP and allied works at Head work site for Augmentation of Gadpukuria (Zone-I) water Supply Scheme under Bongaon Sub-Division, Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001542/2023-2024 | 13/BD | 02/01/2024 | 01/01/2025 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 77.74 | 70.84 | 91.13 | 100
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC | SM/11761 | Augmentation | Acceptance cum work order for Construction of Boundary wall at Head work site for Augmentation of Gadpukuria (Zone-I) water Supply scheme, Bagdah Block within jurisdiction of Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001472/2023-2024 | 4411/BD | 10/11/2023 | 09/01/2024 | GHOSH CONSTRUCTION. | 19.46 | 19.43 | 99.88 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC | SM/11761 | Augmentation | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Gadpukuria (Zone-I) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001493/2023-2024 | 4462/BD | 21/11/2023 | 14/12/2023 | A.D.ENTERPRISE. | 11.48 | 11.45 | 99.76 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC | SM/11761 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional Household Tap Connection (FHTC) for augmentation of Gadpukuria (Zone-I) Water Supply Scheme under Bongaon Sub-Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000048/2023-2024 | 1396/BD | 08/05/2023 | 23/10/2025 | M/S DIPAK ENTERPRISE | 343.41 | 259.65 | 75.61 | 90
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC | SM/11761 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at P.H. No.-II ,ZONE-I (Replacement TUBE WELL) under Gadpukuria ground water based w/s scheme under Block_ Bagdah Dist. - 24Pgs(N) under EMSD-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000599/2024-2025 | 2534/EMD | 28/10/2024 | 27/11/2024 | BIJAN ENTERPRISE | 11.78 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC | SM/11761 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at P.H. No.-I and II ,ZONE-II (NEW TUBE WELL) under Gadpukuria ground water based w/s scheme under Block_ Bagdah Dist. - 24Pgs(N) under EMSD-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000600/2024-2025 | 2535/EMD | 28/10/2024 | 01/03/2025 | JAGANNATH ENTERPRISE | 23.56 | 0 | 0 | 95
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC | SM/11761 | Augmentation | Acceptance cum work order for Additional laying of UPVC pipe to connect every house hold FHTC with Augmentation work at Gadpukuria (Zone-I) W/S Scheme under Bagdah Block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000022/2025-2026 | 1699/BD | 23/05/2025 | 22/07/2025 | THE TOWER CONSTRUCTION | 14.88 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC | SM/11761 | Augmentation | Acceptance cum work order for Repairing and repairing work for 500cum capacity 20mtr. staging height R.C.C Over Head Reservoir for Augmentation of Gadpukur (Zone-I) Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000017/2024-2025 | 1536/BD | 07/06/2024 | 22/07/2024 | ONKAR ENTERPRISE. | 20.09 | 0 | 0 | 100
Total | [13 empty] | 552.23 | 375.2 | 67.94