## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC | SM/11762 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Gadpukuria (Zone-II) Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002777/2021-2022 | 129/Bon | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.73 | 3.73 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC | SM/11762 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000109/2022-2023 | 3686/BD | 14/12/2022 | 14/12/2022 | Resource Division | 76.22 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC | SM/11762 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing (FHTC) for augmentation of Gadpukuria (Zone-II) Water Supply Scheme, under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000013/2023-2024 | 1683/BD | 07/06/2023 | 25/08/2025 | DEBAPRASAD MONDAL. | 368.15 | 144.66 | 39.29 | 60
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC | SM/11762 | Augmentation | Acceptance cum work order for Construction of Boundary wall at Head work site for Augmentation of Gadpukuria (Zone-II) water Supply scheme, Bagdah Block within jurisdiction of Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001478/2023-2024 | 4410/BD | 10/11/2023 | 09/01/2024 | PRABIR KUMAR MONDAL. | 15.9 | 10.04 | 63.16 | 85
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC | SM/11762 | Augmentation | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and Construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Gadpukuria (Zone-II) water Supply scheme, Bagdah Block within jurisdiction of Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001496/2023-2024 | 4486/BD | 23/11/2023 | 10/01/2025 | MA CONSTRUCTION. | 9.25 | 0 | 0 | 45
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC | SM/11762 | Augmentation | Acceptance cum work order for Hiring Diesel Luxury Car on Daily basis ( from 01.01.2024 to 31.03.2024) for the office use of Deputy Superintending Engineer, Planning Circle-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001624/2023-2024 | 4876/BD | 29/12/2023 | 29/03/2024 | M/S B.K.ENTERPRISE. | 0.43 | 1.03 | 237.24 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC | SM/11762 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. Tube well 250 mtr deep by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Gadpukuria (Zone - II) Water Supply Scheme at H/W Site & 2nd T/W Site under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001014/2023-2024 | 2831/BD | 15/09/2023 | 14/11/2023 | B.M.ENGINEERING. & CONSTRUCTION. | 32.24 | 27.49 | 85.27 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC | SM/11762 | Augmentation | Hiring of Luxury Car (Diesel/Driven) for the office use of the Assistant Engineer Bongaon Sub-Division, P.H.E. Dte. Under Barasat Division P.H.E. Dte. (Period from:- 01/08/2023 to 31/01/ 2024). | Assistant Engineer |  | ORD/001199/2023-2024 | 591/Bon | 31/07/2023 | 31/01/2024 | ROY ENGINEERS. | 0.87 | 1.67 | 191.8 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC | SM/11762 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000092/2023-2024 | 1860/BD | 23/06/2023 | 23/06/2023 | Resource Division | 5.56 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC | SM/11762 | Augmentation | Acceptance cum work order for Hiring Diesel Luxury Car on Daily basis for the office use of Deputy Superintending Engineer, Planning Circle-I, PHE Dte.(01-04-2024 to 30-06-2024). | Assistant Engineer | Junior Engineer | ORD/002056/2023-2024 | 926/BD | 15/03/2024 | 14/06/2024 | M/S B.K.ENTERPRISE. | 0.43 | 1.02 | 235.32 | 100
11 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC | SM/11762 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at P.H. No.-I and II ,ZONE-II (NEW TUBE WELL) under Gadpukuria ground water based w/s scheme under Block_ Bagdah Dist. - 24Pgs(N) under EMSD-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000600/2024-2025 | 2535/EMD | 28/10/2024 | 01/03/2025 | JAGANNATH ENTERPRISE | 23.56 | 0 | 0 | 95
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC | SM/11762 | Augmentation | Acceptance cum work order for Withdrawing & relaying of existing UPVC distribution system along the same alignment due to widening and strengthening of Zilla Parishad road from Buzar Bagee Kalitala to Chatar Bagee inconnection with augmentation work at Godpukuria (Zone-II) W/S Scheme under Bagdah block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001790/2023-2024 | 652/BD | 29/02/2024 | 30/03/2024 | R.K.MANDAL & CO. | 8.92 | 8.81 | 98.74 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC | SM/11762 | Augmentation | Acceptance cum work order for Construction of 5.40 mtr. X 3.60mtr. size Switch room with sanitary and water supply arrangement incl. plinth protection at Head Work site at Gadpukuria w/s scheme (Zone-II), Bagdah Block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002212/2023-2024 | 608/BD | 23/02/2024 | 08/04/2024 | UPWARDS ENGINEERING PRIVATE LIMITED. | 5.57 | 5.57 | 99.96 | 100
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC | SM/11762 | Augmentation | Construction of 3.60 mtr. X 3.00mtr. size Switch room with sanitary and water supply arrangement incl. plinth protection at 2nd Tube Well site at Gadpukuria w/s scheme (Zone-II), Bagdah block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002273/2023-2024 | 210/Bon | 27/02/2024 | 12/04/2024 | ONKAR ENTERPRISE. | 4.35 | 4.35 | 99.99 | 100
15 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC | SM/11762 | Augmentation | New service connection at P.H.No- I,Zone-II of Gadpukuria water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). |  |  | BILL/05526/2023-2024 | BP-350-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.04 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC | SM/11762 | Augmentation | New service connection at P.H.No- II,Zone-II of Gadpukuria water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). |  |  | BILL/05525/2023-2024 | BP-349-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5 | 0 | 0 | 0
17 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC | SM/11762 | Augmentation | Additional quotation for New service connection at P.H.No- I ,Zone -II of Godpukuria water supply scheme under EMSD-I ,PHE Dte. In the Dist.- 24Pgs(N) |  |  | BILL/02401/2024-2025 | BP-212 | 09/01/2025 | 09/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.31 | 0 | 0 | 0
Total | [13 empty] | 571.54 | 208.37 | 36.46