## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kapileswarpur to accommodate FHTC | SM/11763 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Kapileswarpur Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002759/2021-2022 | 445/ BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.04 | 4.04 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kapileswarpur to accommodate FHTC | SM/11763 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Kapileswarpur water supply scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000736/2022-2023 | 3305/BD | 10/11/2022 | 08/02/2023 | KINGS & CO. | 240.31 | 205.3 | 85.43 | 90
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kapileswarpur to accommodate FHTC | SM/11763 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000149/2022-2023 | 3810/BD | 23/12/2022 | 23/12/2022 | Resource Division | 2.38 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kapileswarpur to accommodate FHTC | SM/11763 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Kapileswarpur W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001894/2023-2024 | 6756/EMD | 28/11/2023 | 01/04/2025 | M/S DAS ENTERPRISE | 26.73 | 4.17 | 15.59 | 60
Total | [13 empty] | 273.45 | 213.5 | 78.08