## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC | SM/11764 | Augmentation | Route Survey, Design Drawing & DPR Preparation for GOBINDAPUR Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002517/2021-2022 | 443 / BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.76 | 4.76 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC | SM/11764 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000112/2022-2023 | 3699/BD | 14/12/2022 | 14/12/2022 | Resource Division | 26.46 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC | SM/11764 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000188/2022-2023 | 600/BD | 23/02/2023 | 23/02/2023 | Resource Division | 9.36 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC | SM/11764 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 1244/BD | 25/04/2023 | 25/04/2023 | Resource Division | 158.92 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC | SM/11764 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 1628/BD | 01/06/2023 | 01/06/2023 | Resource Division | 9.42 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC | SM/11764 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Gobindapur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000781/2022-2023 | 3488/BD | 02/12/2022 | 02/03/2023 | M/S NIRMAN CONSTRUCTION. | 341.88 | 30.04 | 8.79 | 99
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC | SM/11764 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Gabindapur Water Supply Scheme (H/W Site) within the Jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001166/2023-2024 | 2921/BD | 26/09/2023 | 26/10/2023 | B.M.ENGINEERING. & CONSTRUCTION. | 16.13 | 13.5 | 83.7 | 29
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC | SM/11764 | Augmentation | Regarding Restoration charges for road damages. |  |  | BILL/03466/2023-2024 | BP-2023-24-830 | 15/03/2024 | 15/03/2024 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 13.3 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC | SM/11764 | Augmentation | Regarding Restoration charges for road damages. |  |  | BILL/03469/2023-2024 | BP-2023-24-830 | 15/03/2024 | 15/03/2024 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 8.79 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC | SM/11764 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Gobindapur water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001007/2022-2023 | 170/BD | 19/01/2023 | 26/05/2025 | KINGS & CO. | 437.87 | 122.72 | 28.03 | 66
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC | SM/11764 | Augmentation | Acceptance cum work order for Construction of Boundary Wall at the site of Pump House -III of Gobindapur Water Supply Scheme under Basirhat Sub-Division within Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001039/2024-2025 | 58/BD | 07/01/2025 | 07/05/2025 | IKBAL HOSSAIN | 14.35 | 0 | 0 | 60
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC | SM/11764 | Augmentation | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at OHR site under Augmentation work at Gobindapur W/S Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000040/2025-2026 | 1697/BD | 23/05/2025 | 20/09/2025 | M/S B.K.ENTERPRISE. | 20.9 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC | SM/11764 | Augmentation | Acceptance cum work order for Construction of Boundary wall, Approach Road and plinth protection of Pump House at Head Work site of Gobindapur Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000073/2025-2026 | 1769/BD | 29/05/2025 | 26/09/2025 | RAKESH ENTERPRISE. | 24.5 | 0 | 0 | 0
Total | [13 empty] | 1086.64 | 171.02 | 15.74