## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nityananda Kati Balti to accommodate FHTC | SM/11974 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Nityanadakati Balti Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002761/2021-2022 | 440/ BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.69 | 3.69 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nityananda Kati Balti to accommodate FHTC | SM/11974 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000203/2022-2023 | 860/BD | 20/03/2023 | 20/03/2023 | Resource Division | 60.86 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nityananda Kati Balti to accommodate FHTC | SM/11974 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000150/2023-2024 | 4411/BD | 10/11/2023 | 10/11/2023 | Resource Division | 7.39 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nityananda Kati Balti to accommodate FHTC | SM/11974 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Nityananda Kati Balti water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001141/2022-2023 | 514/BD | 20/02/2023 | 27/03/2025 | UTPAL CONSTRUCTION & CO. | 272.4 | 223.13 | 81.91 | 52
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Nityananda Kati Balti to accommodate FHTC | SM/11974 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II(Rep.) under Nityananda-Katibalti W/S Scheme District of 24 Pgs. (N) |  |  | ORD/002685/2023-2024 | 4988/EMD | 22/08/2023 | 21/09/2023 | SANKAR PRASAD DUTTA & CO | 13.17 | 0 | 0 | 0
Total | [13 empty] | 357.51 | 226.82 | 63.44