## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 180 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Barunhat Patlikhanpur w/s scheme (Z-II), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000027/2023-2024 | 1218/BD | 20/04/2023 | 20/05/2023 | ANJALI ENTERPRISE. | 25.41 | 17.83 | 70.18 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 180 mtr deep Tubewell by D.R. Rig method at PH No.- 1 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Barunhat Patlikhanpur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000028/2023-2024 | 1219/BD | 20/04/2023 | 20/05/2023 | ANJALI ENTERPRISE. | 12.7 | 9.5 | 74.81 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Barunhat Patlikhanpur water supply scheme (Z-I), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001150/2022-2023 | 699/BD | 03/03/2023 | 01/06/2023 | MONDAL & CO. (BASIRHAT). | 417.62 | 406.32 | 97.29 | 48
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2 (Size-3.60x3.00 mtr.) for Augmentation of Barunhat Patlikhanpur w/s scheme (Z-II), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000080/2023-2024 | 1428/BD | 11/05/2023 | 10/07/2023 | JESMINE ENTERPRISE. | 17.34 | 17.15 | 98.94 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Acceptance cum work order for Repairing of pump house with boundary wall & other allied works at PH No.-1 of Barunhat Patlikhanpur w/s scheme, Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000303/2023-2024 | 2117/BD | 19/07/2023 | 09/08/2023 | M/S K.B.ENTERPRISE. | 7.39 | 7.32 | 99.06 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Acceptance cum work order for Construction of new stand post for Barunhat patlikhanpur w/s Scheme, Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte | Assistant Engineer |  | ORD/000308/2023-2024 | 829/HSD | 14/07/2023 | 24/07/2023 | PRASANTA MITRA. | 2.89 | 2.89 | 99.82 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000234/2022-2023 | 935/BD | 22/03/2023 | 22/03/2023 | Resource Division | 80.45 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | New service connection under AE-I Barunhat Siristala |  |  | BILL/01868/2023-2024 | BP-122-23-24 | 07/08/2023 | 07/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.47 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | New Service Connection under AE-I Barunhat |  |  | BILL/01869/2023-2024 | BP-123-23-24 | 07/08/2023 | 07/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 16.13 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Barunhat Patlikhanpur water supply scheme (Zone-II), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000946/2022-2023 | 87/BD | 11/01/2023 | 11/04/2023 | R.K.MANDAL & CO. | 317.9 | 310.72 | 97.74 | 80
11 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II (Rep.) and III and IV (New) under Barunhat-Patlikhanpur W/S Scheme District of 24 Pgs. (N) NIET No.- 29 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer | ORD/001973/2022-2023 | 1287/EMD | 28/03/2023 | 27/04/2023 | S.G. ENTERPRISE | 52.98 | 49.17 | 92.81 | 45
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Formal work order for Construction of 500cum capacity 20mtr staging height R.C.C Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Barunhat Patlikhanpur water supply Scheme(Z-I), Hasnabad Block under Hasnabad Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000751/2023-2024 | 2611/BD | 29/08/2023 | 28/08/2024 | MONDAL & CO. (BASIRHAT). | 203.7 | 185.49 | 91.06 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no-1 in connection with Augmentation of Barunhat Patlikhanpur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001859/2023-2024 | 38/HSD | 09/01/2024 | 19/01/2024 | SHYAM SUNDAR DAS. | 0.93 | 0.88 | 94.1 | 100
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Formal work order for Additional Laying of DI/UPVC distribution pipe line and Providing Functional Household Tap Connection for the left out portion in connection with Augmentation of Baruhat Patlikhanpur water supply scheme (Z-I), Hasnabad Block of Hasnabad Sub-Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000097/2024-2025 | 1735/BD | 27/06/2024 | 25/09/2024 | MONDAL & CO. (BASIRHAT). | 107.74 | 69.79 | 64.78 | 70
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Acceptance cum work order for Emergent resting of old rising main pipeline with UC Bullah pilling at OHR site in connection with augmentation io Barunhat Patlikhanpur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub- Division P.H.E. Dte. |  |  | ORD/001452/2024-2025 | 326/HSD | 04/02/2025 | 14/02/2025 | MONDAL & CO. (BASIRHAT). | 0.98 | 0 | 0 | 0
Total | [13 empty] | 1270.63 | 1077.07 | 84.77