## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 180 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Barunhat Patlikhanpur w/s scheme (Z-II), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000027/2023-2024 | 1218/BD | 20/04/2023 | 20/05/2023 | ANJALI ENTERPRISE. | 25.41 | 17.83 | 70.18 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 180 mtr deep Tubewell by D.R. Rig method at PH No.- 1 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Barunhat Patlikhanpur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000028/2023-2024 | 1219/BD | 20/04/2023 | 20/05/2023 | ANJALI ENTERPRISE. | 12.7 | 9.5 | 74.81 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Barunhat Patlikhanpur water supply scheme (Z-I), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001150/2022-2023 | 699/BD | 03/03/2023 | 01/06/2023 | MONDAL & CO. (BASIRHAT). | 417.62 | 406.32 | 97.29 | 48
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2 (Size-3.60x3.00 mtr.) for Augmentation of Barunhat Patlikhanpur w/s scheme (Z-II), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000080/2023-2024 | 1428/BD | 11/05/2023 | 10/07/2023 | JESMINE ENTERPRISE. | 17.34 | 17.15 | 98.94 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Acceptance cum work order for Repairing of pump house with boundary wall & other allied works at PH No.-1 of Barunhat Patlikhanpur w/s scheme, Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000303/2023-2024 | 2117/BD | 19/07/2023 | 09/08/2023 | M/S K.B.ENTERPRISE. | 7.39 | 7.32 | 99.06 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Acceptance cum work order for Construction of new stand post for Barunhat patlikhanpur w/s Scheme, Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte | Assistant Engineer |  | ORD/000308/2023-2024 | 829/HSD | 14/07/2023 | 24/07/2023 | PRASANTA MITRA. | 2.89 | 2.89 | 99.82 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000234/2022-2023 | 935/BD | 22/03/2023 | 22/03/2023 | Resource Division | 80.45 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | New service connection under AE-I Barunhat Siristala |  |  | BILL/01868/2023-2024 | BP-122-23-24 | 07/08/2023 | 07/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.47 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | New Service Connection under AE-I Barunhat |  |  | BILL/01869/2023-2024 | BP-123-23-24 | 07/08/2023 | 07/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 16.13 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Barunhat Patlikhanpur water supply scheme (Zone-II), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000946/2022-2023 | 87/BD | 11/01/2023 | 11/04/2023 | R.K.MANDAL & CO. | 317.9 | 310.72 | 97.74 | 80
11 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II (Rep.) and III and IV (New) under Barunhat-Patlikhanpur W/S Scheme District of 24 Pgs. (N) NIET No.- 29 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer | ORD/001973/2022-2023 | 1287/EMD | 28/03/2023 | 27/04/2023 | S.G. ENTERPRISE | 52.98 | 49.17 | 92.81 | 45
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Formal work order for Construction of 500cum capacity 20mtr staging height R.C.C Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Barunhat Patlikhanpur water supply Scheme(Z-I), Hasnabad Block under Hasnabad Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000751/2023-2024 | 2611/BD | 29/08/2023 | 28/08/2024 | MONDAL & CO. (BASIRHAT). | 203.7 | 185.49 | 91.06 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no-1 in connection with Augmentation of Barunhat Patlikhanpur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001859/2023-2024 | 38/HSD | 09/01/2024 | 19/01/2024 | SHYAM SUNDAR DAS. | 0.93 | 0.88 | 94.1 | 100
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Formal work order for Additional Laying of DI/UPVC distribution pipe line and Providing Functional Household Tap Connection for the left out portion in connection with Augmentation of Baruhat Patlikhanpur water supply scheme (Z-I), Hasnabad Block of Hasnabad Sub-Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000097/2024-2025 | 1735/BD | 27/06/2024 | 25/09/2024 | MONDAL & CO. (BASIRHAT). | 107.74 | 69.79 | 64.78 | 70
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Acceptance cum work order for Emergent resting of old rising main pipeline with UC Bullah pilling at OHR site in connection with augmentation io Barunhat Patlikhanpur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub- Division P.H.E. Dte. |  |  | ORD/001452/2024-2025 | 326/HSD | 04/02/2025 | 14/02/2025 | MONDAL & CO. (BASIRHAT). | 0.98 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Formal work order for Construction of 350 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Barunhat Patlikhanpur water supply scheme (Z-II), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001097/2023-2024 | 2867/BD | 20/09/2023 | 01/03/2025 | R.K.MANDAL & CO. | 152.42 | 74.03 | 48.57 | 100
17 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with augmentation of Barunhat Patlikhanpur water supply scheme (Z-I), Hasnabd block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001399/2024-2025 | 265/HSD | 30/01/2025 | 09/02/2025 | STAR CONSTRUCTION. | 0.55 | 0 | 0 | 100
18 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Acceptance cum work order for Special Repair & Maintenance of Rising main & Distribution system (CI/DI/UPVC) with construction of new stand post for Barunhat Patlikhanpur w/s Scheme, Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002098/2024-2025 | 577/HSD | 17/03/2025 | 27/03/2025 | STAR CONSTRUCTION. | 2.15 | 0 | 0 | 100
19 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | SM/11987 | Augmentation | Acceptance cum work order for Sand filling at ditch area for construction of temporary approach road for movement of winch machine and other allied machineries at OHR site within Barunhat Patlikhanpur W/S scheme (Z-I), Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000285/2025-2026 | 1495/HSD | 14/07/2025 | 24/07/2025 | TRISHA ENTERPRISE & CO. | 0.97 | 0 | 0 | 100
Total | [13 empty] | 1426.72 | 1151.1 | 80.68