## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC | SM/12111 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Durgapur Baylani w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000022/2023-2024 | 1208/BD | 20/04/2023 | 20/05/2023 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 21.47 | 0 | 0 | 91
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC | SM/12111 | Augmentation | Formal work order for the work of Laying of Di/UPVC distribution pipe line, construction of 500cum capacity 20mtr staging height R.C.C over Head Reservoir as per Deptt. design, drawing & specification including bored pile with pile cap and providing Functional Household Tap Connection in connection with Augmentation of Durgapur Baylani Water Supply Scheme(Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000682/2023-2024 | 2458/BD | 17/08/2023 | 17/08/2026 | APURBA MANDAL | 844.5 | 0 | 0 | 71
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC | SM/12111 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Durgapur Baylani w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000738/2023-2024 | 2492/BD | 18/08/2023 | 17/09/2023 | M/S RAJPATH CONSTRUCTION. | 21.95 | 0 | 0 | 66
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC | SM/12111 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I)(Rep) under Durgapur- Baylani W/S Scheme District of 24 Pgs. (N) NIET No. 26 of EE/EMD of 2022-23 (Sl. No.-23) | Assistant Engineer | Junior Engineer | ORD/001899/2022-2023 | 1169/EMD | 21/03/2023 | 01/05/2025 | ABHISEK ENGINEERING CONCERN | 26.35 | 0 | 0 | 80
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC | SM/12111 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Durgapur Baylani Z-I w/s scheme, Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001377/2024-2025 | 244/HSD | 30/01/2025 | 09/02/2025 | M/S RAJPATH CONSTRUCTION. | 0.63 | 0 | 0 | 100
Total | [13 empty] | 914.9 | 0 | 0