## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | supply & installation of LED Sing board P.H. no. I (Zone-I&II) of Rupmari w/s scheme 24Pgs(N) |  |  | ORD/001175/2020-2021 | 1411/EMSD I | 10/07/2020 | 23/07/2020 | S.P. ENTERPRISE | 0.4 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of RUPMARI Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002687/2021-2022 | 228/HSD | 02/02/2022 | 17/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.81 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Acceptance cum work order for Additional Survey Work For DPR Preparation of Augmentation of RUPMARI Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002700/2021-2022 | 229/HSD | 02/02/2022 | 17/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.04 | 0 | 0 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Rupmari w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000021/2023-2024 | 1207/BD | 20/04/2023 | 20/05/2023 | M/S PROGATI ENTERPRISE. | 42.94 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Acceptance cum work order for Construction of boundary wall at Pump House No-1, 2 & 5 for damaged portion and repairing of existing boundary wall within Rupmari w/s scheme, Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000283/2023-2024 | 822/HSD | 14/07/2023 | 29/07/2023 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.38 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Acceptance cum work order for Pump connection at PH No-5 & other allied works for Augmentation of Rupmari w/s scheme, Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000755/2022-2023 | 616/HSD | 07/04/2022 | 22/04/2022 | GOBINDA DAS. | 1.97 | 0 | 0 | 1
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Rupmari w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000018/2023-2024 | 1204/BD | 20/04/2023 | 20/05/2023 | M/S DATTA ENTERPRISE. | 42.94 | 0 | 0 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Acceptance cum work order for Construction of boundary wall at Pump House No-1, 2 & 5 for damaged portion and repairing of existing boundary wall within Rupmari w/s scheme, Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000284/2023-2024 | 822/HSD | 14/07/2023 | 29/07/2023 | ANKUSH CONSTRUCTION & CO. | 4.38 | 0 | 0 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no-5 in connection with Augmentation of Rupmari w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000260/2023-2024 | 786/HSD | 13/07/2023 | 23/07/2023 | SARKAR ENTERPRISE | 0.88 | 0 | 0 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000175/2022-2023 | 519/BD | 20/02/2023 | 20/02/2023 | Resource Division | 145.86 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Zone-I and II) )(Rep.) under Rupmari W/S Scheme District of 24 Pgs. (N) NIET No.- 32 of EE/EMD of 2022-23 (Sl. No.- 22) | Assistant Engineer | Junior Engineer | ORD/001674/2022-2023 | 1012/EMD | 09/03/2023 | 08/04/2023 | CREATIVE WATER & PROCESS TECHNOLOGIES PVT. LTD. | 79.43 | 0 | 0 | 85
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Acceptance cum work order for Construction of Office cum Godown with sanitary & water supply arrangement i/c plinth protection at OHR site (Size-5.40x3.60 mtr.) for Augmentation of Rupamari w/s scheme (Z-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000542/2024-2025 | 2974/BD | 04/10/2024 | 03/12/2024 | TALUKDER & CO. | 13.56 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Rupmari (Zone-II water supply scheme, Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001120/2022-2023 | 405/BD | 09/02/2023 | 10/05/2023 | M/S NIRMAN CONSTRUCTION. | 345.89 | 0 | 0 | 1
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and Providing Functional Household Tap Connection in Connection with Augmentation of Rupmari water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001068/2022-2023 | 403/BD | 09/02/2023 | 10/05/2023 | M/S DATTA ENTERPRISE. | 348.91 | 0 | 0 | 85
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Rupmari w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000730/2023-2024 | 2479/BD | 18/08/2023 | 17/09/2023 | ABDUL ALIM MONDAL. | 25.81 | 0 | 0 | 77
16 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 150 mm dia DI pipeline at different places in connection with Augmentation of Rupmari w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001832/2023-2024 | 261/HSD | 06/03/2024 | 16/03/2024 | M/S NIRMAN CONSTRUCTION. | 0.93 | 0 | 0 | 100
17 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site in connection with Augmentation of Rupmari w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001850/2023-2024 | 275/HSD | 06/03/2024 | 16/03/2024 | SARKAR ENTERPRISE & CO. | 0.83 | 0 | 0 | 79
18 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 150 mm dia DI pipeline at different places in connection with Augmentation of Rupmari w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001833/2023-2024 | 262/HSD | 06/03/2024 | 16/03/2024 | M/S DATTA ENTERPRISE. | 0.93 | 0 | 0 | 85
19 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 100 mm dia DI pipeline at different places in connection with Augmentation of Rupmari w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001834/2023-2024 | 264/HSD | 06/03/2024 | 16/03/2024 | M/S DATTA ENTERPRISE. | 0.93 | 0 | 0 | 85
20 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 100 mm dia DI pipeline at different places in connection with Augmentation of Rupmari w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000310/2024-2025 | 881/HSD | 07/08/2024 | 17/08/2024 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 0.93 | 0 | 0 | 100
21 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Acceptance cum work order for Construction of Office cum Godown with sanitary & water supply arrangement i/c plinth protection at OHR site (Size-5.40x3.60 mtr.) for Augmentation of Rupamari w/s scheme (Z-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000547/2024-2025 | 3023/BD | 22/10/2024 | 17/10/2025 | LAHIRI CONSTRUCTION. | 13.58 | 0 | 0 | 50
22 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Rupmari water supply scheme (Zone - I), Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000243/2023-2024 | 2031/BD | 13/07/2023 | 21/07/2025 | SARKAR ENTERPRISE & CO. | 114.21 | 0 | 0 | 100
23 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Rupmari water supply scheme (Zone - II), Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000244/2023-2024 | 2032/BD | 13/07/2023 | 30/03/2025 | DEBAPRASAD MONDAL. | 114.2 | 0 | 0 | 85
24 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | SM/12122 | Augmentation | Formal work order for Protection works for protection of UPVC distribution pipe line at different places and other allied works in connection with Augmentation of Rupmari w/s scheme (Z-I & II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000415/2024-2025 | 2866/BD | 30/09/2024 | 28/01/2025 | UTPAL CONSTRUCTION & CO. | 132.55 | 0 | 0 | 100
Total | [13 empty] | 1442.3 | 0 | 0