## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC | SM/12124 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.III and IV(Rep) under Hasnabad W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/000078/2023-2024 | 1972/EMD | 07/06/2023 | 07/07/2023 | GHOSE ENGINEERING SYNDICATE | 26.5 | 10.61 | 40.02 | 50
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC | SM/12124 | Augmentation | Acceptance cum work order for Providing Functional tap connection at Rameswarpur Union Adarsha Bidyalaya at Rameswarpur in connection with augmentation of Hasnabad w/s scheme, Hasnabad block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/000864/2023-2024 | 1050/HSD | 01/09/2023 | 11/09/2023 | SARKAR ENTERPRISE | 0.6 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC | SM/12124 | Augmentation | Acceptance cum work order for Construction of boundary wall at North side for damaged portion, construction of approach road & other allied works at PH No-2 within Hasnabad w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000282/2023-2024 | 821/HSD | 14/07/2023 | 24/07/2023 | SARKAR ENTERPRISE | 3.87 | 3.87 | 99.94 | 100
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC | SM/12124 | Augmentation | Acceptance cum work order for Construction of approach road, North side boundary wall & other allied works at PH no-1 within Hasnabad w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000281/2023-2024 | 820/HSD | 14/07/2023 | 04/08/2023 | ABDUL ALIM MONDAL. | 2.73 | 2.69 | 98.35 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC | SM/12124 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000240/2022-2023 | 932/BD | 22/03/2023 | 22/03/2023 | Resource Division | 221.49 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC | SM/12124 | Augmentation | Acceptance cum work order for Arrangement Of Block Level Orientation programe involving stakeholders of PRI bodies including refreshments, training materials and related activities for 2 nos Blocks ( Hasnabad & Hingalganj) in North 24 Parganas under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000171/2024-2025 | 754/HSD | 19/07/2024 | 29/07/2024 | IMAGIN | 0.98 | 0.98 | 100 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC | SM/12124 | Augmentation | Formal work order for "Laying of DI rising main, DI/UPVC distribution pipe line, Construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and providing Functional Household Tap Connection in connection with Augmentaion of Hasnabad water supply scheme, Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000779/2023-2024 | 2601/BD | 28/08/2023 | 01/04/2025 | M/S S.S.ENTERPRISE. (SOUTH) | 793.69 | 378.08 | 47.64 | 70
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC | SM/12124 | Augmentation | Acceptance cum work order for Withdrawing, relaying of different dia. UPVC pipe line at Chaktangramari para in connection with augmentation of Hasnabad water supply scheme under Hasnabad Sub-Division, P.H.E.Dte. |  |  | ORD/000168/2025-2026 | 1005/HSD | 04/06/2025 | 14/06/2025 | SARKAR ENTERPRISE | 0.95 | 0 | 0 | 0
Total | [13 empty] | 1050.82 | 396.22 | 37.71