## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC | SM/12125 | Augmentation | Acceptance cum work order for Construction of boundary wall for Back & Left side at PH No.-1 within Kanaikati Kathalberia w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000436/2022-2023 | 1362/HSD | 03/08/2022 | 24/08/2022 | BADAL GHOSH. | 3.87 | 3.84 | 99.37 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC | SM/12125 | Augmentation | Acceptance cum work order for Emergent fencing work for protecting the adjacent land of PH no-1 within Kanaikati Kathalberia w/s scheme (Z-I), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/000267/2023-2024 | 793/HSD | 13/07/2023 | 23/07/2023 | NEW LIFE CONSTRUCTION. | 0.91 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC | SM/12125 | Augmentation | Acceptance cum work order for Construction of boundary wall for Front & Right side at PH No.-1 within Kanaikati Kathalberia w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000437/2022-2023 | 1363/HSD | 03/08/2022 | 24/08/2022 | LAHIRI CONSTRUCTION. | 3.34 | 3.33 | 99.74 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC | SM/12125 | Augmentation | Acceptance cum work order for Construction of boundary wall for right & back side at PH No.-2 within Kanaikati Kathalberia w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000438/2022-2023 | 1364/HSD | 03/08/2022 | 24/08/2022 | STAR CONSTRUCTION. | 3.26 | 3.23 | 99.18 | 1
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC | SM/12125 | Augmentation | Acceptance cum work order for Construction of boundary wall for front & left side at PH No.-2 within Kanaikati Kathalberia w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000439/2022-2023 | 1365/HSD | 03/08/2022 | 24/08/2022 | STAR CONSTRUCTION. | 2.66 | 2.66 | 99.78 | 1
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC | SM/12125 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kanaikati Kathalberia w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001178/2022-2023 | 791/BD | 13/03/2023 | 12/04/2023 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 26.26 | 18.02 | 68.61 | 7
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC | SM/12125 | Augmentation | Acceptance cum work order for Repairing of pump house & construction of approach road with cement concrete at PH No.-2 for Kanaikati Kathalberia w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000302/2023-2024 | 2116/BD | 19/07/2023 | 03/08/2023 | M/S K.B.ENTERPRISE. | 5.59 | 5.35 | 95.69 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC | SM/12125 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000252/2022-2023 | 916/BD | 22/03/2023 | 22/03/2023 | Resource Division | 13.65 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC | SM/12125 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap connection for Augmentation of Kanaikati Kathalberia water Supply Scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001190/2023-2024 | 4201/BD | 31/10/2023 | 23/04/2025 | KINGS & CO. | 707.01 | 538.15 | 76.12 | 80
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC | SM/12125 | Augmentation | Acceptance cum work order for Construction of 150 cum capacity CWR , pipe connection and cost of pipes, specials for Augmentation of Kanaikati Kathalberia water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, P.H.E Dte. | Assistant Engineer |  | ORD/000402/2024-2025 | 2520/BD | 02/09/2024 | 01/03/2025 | SARKAR ENTERPRISE & CO. | 43.88 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC | SM/12125 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I) (Rep.) under Kanaikathi-Kanthalberia W/S Scheme District of 24 Pgs. (N) NIET No.- 27 of EE/EMD of 2022-23 (Sl. No.- 21) | Assistant Engineer | Junior Engineer | ORD/001934/2022-2023 | 1233/EMD | 24/03/2023 | 23/04/2023 | GLACIER ENGINEERING CO. | 27.79 | 23.98 | 86.31 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC | SM/12125 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kanaikati Kathalberia w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000742/2023-2024 | 2494/BD | 18/08/2023 | 17/09/2023 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 26.9 | 20.67 | 76.85 | 33
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC | SM/12125 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line and Providing Functional Household Tap Connection for the leftout portion in connection with Augmentation of Kanaikathi Kathalberia water supply scheme (Z-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000414/2024-2025 | 3051/BD | 24/10/2024 | 23/11/2024 | KINGS & CO. | 101.79 | 0 | 0 | 0
Total | [13 empty] | 966.89 | 619.23 | 64.04