## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC | SM/12126 | Augmentation | Acceptance cum work order for Laying of 50 mm dia. UPVC pipe line for providing 3 nos. tap connection at near Sulkuni Abad area within Bhabanipur W/S Scheme, Hasnabad block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000296/2023-2024 | 792/HSD | 13/07/2023 | 20/07/2023 | M/S K.B.ENTERPRISE. | 0.86 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC | SM/12126 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Zone-II) (Rep.) under Bhawanipur W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001151/2023-2024 | 4754/EMD | 07/08/2023 | 06/09/2023 | A.G ENTERPRISE. | 41.41 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC | SM/12126 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000235/2022-2023 | 911/BD | 22/03/2023 | 22/03/2023 | Resource Division | 348.37 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC | SM/12126 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, construction of 400cum capacity 20mtr staging height R.C.C Over head Reservoir as per Dept. design, drawing & specification including bored pile with pile cap and providing Functional Household Tap connection in connection with Augmentation of Bhabanipur Water Supply Scheme(Zone-I), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000852/2023-2024 | 2651/BD | 01/09/2023 | 01/09/2024 | SUPRITI ENTERPRISE. | 867.51 | 216.3 | 24.93 | 45
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC | SM/12126 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bhabanipur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/002031/2023-2024 | 931/BD | 15/03/2024 | 29/04/2024 | AAHAN CONSTRUCTION | 59.17 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC | SM/12126 | Augmentation | Acceptance cum work order for Sinking of 3 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tube well by D.R. Rig method at PH No.-1, 2 & 3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bhabanipur w/s scheme (Z-II), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001933/2023-2024 | 916/BD | 15/03/2024 | 14/05/2024 | M/S K.P.PAL. | 89.28 | 59.32 | 66.43 | 100
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC | SM/12126 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I) (New) under Bhawanipur W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001150/2023-2024 | 4753/EMD | 07/08/2023 | 06/09/2023 | RMD TRADING | 27.98 | 0 | 0 | 70
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC | SM/12126 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Construction of 600 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and providing Functional Household Tap Connection in connection with Augmentaion of Bhabanipur water supply scheme (Zone-II), Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000784/2023-2024 | 2600/BD | 28/08/2023 | 29/03/2025 | M/S S.S.ENTERPRISE. (SOUTH) | 956.1 | 499.7 | 52.26 | 70
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC | SM/12126 | Augmentation | Acceptance cum work order for Land development at Pump House No-1 in connection with augmentation of Bhabanipur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. |  |  | ORD/000055/2025-2026 | 842/HSD | 15/05/2025 | 25/05/2025 | MD.SALIM GAZI. | 1.49 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC | SM/12126 | Augmentation | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2 (Size-3.60x3.00 mtr.) for Augmentation of Bhabanipur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000026/2025-2026 | 1516/BD | 13/05/2025 | 11/08/2025 | M/S MONDAL CONSTRUCTION | 17.62 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC | SM/12126 | Augmentation | Acceptance cum work order for Emergent Construction of stand post & construction of platforms at Bhurkunda & Bedemari mouza in connection within Bhabanipur w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001895/2024-2025 | 535/HSD | 10/03/2025 | 20/03/2025 | M/S K.B.ENTERPRISE. | 0.97 | 0 | 0 | 100
Total | [13 empty] | 2410.76 | 775.32 | 32.16