## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC | SM/12127 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.III (New) under Helencha W/S Scheme, District of 24 Pgs. (N). |  |  | ORD/001130/2023-2024 | 4722/EMD | 04/08/2023 | 03/09/2023 | M/S. G.P. ENTERPRISE | 10.72 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC | SM/12127 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000155/2022-2023 | 1258/BD | 25/04/2023 | 25/04/2023 | Resource Division | 147.75 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC | SM/12127 | Augmentation | Hiring of an Additional Vehicle (Diesel) for the site inspection of different ongoing schemes under JJM Program at Bongaon Sub-Division, P.H.E.Dte. period from 01.01.2024 to 30.06.2024. | Assistant Engineer | Junior Engineer | ORD/002553/2023-2024 | 1022/Bon | 29/12/2023 | 29/06/2024 | VAI ENTERPRISE. | 0.86 | 1.95 | 226.06 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC | SM/12127 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and Providing (FHTC) for augmentation of Helencha Water Supply Scheme, Bagdah Block, under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001170/2022-2023 | 754/BD | 09/03/2023 | 07/06/2023 | MONDAL ENTERPRISE. (BARASAT) | 684.22 | 678.51 | 99.17 | 100
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC | SM/12127 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Replacement) under Helencha W/S Scheme, District of 24 Pgs. (N). | Assistant Engineer | Junior Engineer | ORD/001131/2023-2024 | 4723/EMD | 04/08/2023 | 03/09/2023 | WESTERN ENGINEERING CO. | 21.41 | 19.67 | 91.88 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC | SM/12127 | Augmentation | Acceptance cum work order for Sinking of 2 (two) no. 300 mm. x 200 mm. dia.250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Helencha Water Supply Scheme (H/W Site & 2nd T/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001117/2023-2024 | 2941/BD | 27/09/2023 | 26/11/2023 | JOY GURU ENTERPRISE | 32.22 | 26.95 | 83.63 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC | SM/12127 | Augmentation | Repairing and renovation of Pump House No.- 3 under Augmentation of Helencha Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000889/2024-2025 | 1396/Bon | 27/11/2024 | 17/12/2024 | KAMAL HALDER. | 1.76 | 1.73 | 98.37 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC | SM/12127 | Augmentation | Health assessment of existing OHR of Helencha PWSS (350 cum) and ancillary structures, Bagdah Block conducting Non-Destructive Test and through visual observation at within the jurisdiction Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000018/2024-2025 | 690/Bon | 07/06/2024 | 22/06/2024 | SIRCON ENGINEERING SERVICES | 4.58 | 4.58 | 100 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC | SM/12127 | Augmentation | Repairing and renovation of Compressor Room for Iron Elimination Plant under Augmentation of Helencha Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. |  | Junior Engineer | ORD/002506/2023-2024 | 640/Bon | 14/08/2023 | 04/09/2023 | MONDAL & CO.(BON) | 1.59 | 1.56 | 97.88 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC | SM/12127 | Augmentation | Hiring of an Additional Vehicle (Diesel) for the site inspection of different ongoing schemes under JJM Program at Bongaon Sub-Division, P.H.E.Dte. period from 01.07.2024 to 31.08.2024. | Assistant Engineer | Junior Engineer | ORD/001065/2024-2025 | 801/Bon | 28/06/2024 | 28/08/2024 | VAI ENTERPRISE. | 0.29 | 0.59 | 200.75 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC | SM/12127 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe and allied works under Augmentation work at Helencha W/S Scheme Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. (Part-B). | Assistant Engineer | Junior Engineer | ORD/000767/2024-2025 | 3267/BD | 25/11/2024 | 21/09/2025 | ABDUL HAMID GAZI. | 27.07 | 0 | 0 | 35
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC | SM/12127 | Augmentation | Hiring of an Additional Vehicle (Diesel) for the site inspection of different Bongaon ongoing schemes under JJM Program at Bongaon Sub-Division, P.H.E.Dte. (Period from:-01/09/2024 to 28/02/ 2025) | Assistant Engineer | Junior Engineer | ORD/001035/2024-2025 | 1076/Bon | 30/08/2024 | 28/02/2025 | PRIYAM ENTERPRISE | 0.86 | 1.75 | 203.95 | 0
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC | SM/12127 | Augmentation | Acceptance cum work order for Repairing & renovation of Boundary wall, Earth Filling, Concreting and Repairing & renovation of 3.60 mtr. X 3.00 mtr. size Pump House with sanitary and water supply arrangement at 2nd TW Site of Helencha Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000077/2025-2026 | 1902/BD | 05/06/2025 | 03/10/2025 | KAMAL HALDER. | 10.52 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC | SM/12127 | Augmentation | Repairing and renovation of 150 Cum C.W.R. for Augmentation of Helencha Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000400/2025-2026 | 817/Bon | 26/06/2025 | 10/08/2025 | KAMAL HALDER. | 2.15 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC | SM/12127 | Augmentation | Construction of Latrine at Head Work site for Augmentation of Helencha Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000610/2025-2026 | 640/Bon | 21/05/2025 | 05/07/2025 | KAMAL HALDER. | 2.4 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC | SM/12127 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Helencha Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001741/2023-2024 | 537/BD | 21/02/2024 | 15/02/2025 | ACHINTA KUMAR HALDER. | 15.42 | 3.99 | 25.89 | 100
17 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC | SM/12127 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe and allied works under Augmentation work at Helencha W/S Scheme Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. (Part-A). | Assistant Engineer | Junior Engineer | ORD/000850/2024-2025 | 3387/BD | 03/12/2024 | 01/06/2025 | KAMAL HALDER. | 11.54 | 0 | 0 | 100
18 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC | SM/12127 | Augmentation | Acceptance cum work order for Repairing and renovation works for 350 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir for Augmentation of Helencha Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000474/2024-2025 | 2686/BD | 18/09/2024 | 31/01/2025 | RAKESH ENTERPRISE. | 17.39 | 6.8 | 39.12 | 100
Total | [13 empty] | 992.77 | 748.08 | 75.35