## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC | SM/12273 | Augmentation | Route Survey, Design Drawing & DPR Preparation for PAIKARDANGA Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001938/2021-2022 | 194/BHTSD | 28/02/2022 | 15/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 100 | 1
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC | SM/12273 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000190/2022-2023 | 602/BD | 23/02/2023 |  | Resource Division | 31.31 | 0 | 0 | 0
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC | SM/12273 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000196/2022-2023 | 854/BD | 20/03/2023 |  | Resource Division | 377.63 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC | SM/12273 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II and III (Rep.) under Paikardanga W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001128/2023-2024 | 4720/EMD | 04/08/2023 | 03/09/2023 | ASHUTOSH DAS & CO. | 26.49 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC | SM/12273 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Paikardanga water supply scheme in Basirhat-I Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001010/2022-2023 | 173/BD | 19/01/2023 | 19/04/2023 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 707.21 | 262.57 | 37.13 | 38
Total | [13 empty] | 1147.48 | 267.41 | 23.3