## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC | SM/12273 | Augmentation | Route Survey, Design Drawing & DPR Preparation for PAIKARDANGA Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001938/2021-2022 | 194/BHTSD | 28/02/2022 | 15/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC | SM/12273 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000196/2022-2023 | 854/BD | 20/03/2023 | 20/03/2023 | Resource Division | 377.63 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC | SM/12273 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000190/2022-2023 | 602/BD | 23/02/2023 | 23/02/2023 | Resource Division | 31.31 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC | SM/12273 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II and III (Rep.) under Paikardanga W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001128/2023-2024 | 4720/EMD | 04/08/2023 | 03/09/2023 | ASHUTOSH DAS & CO. | 26.49 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC | SM/12273 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Paikardanga water supply scheme in Basirhat-I Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001010/2022-2023 | 173/BD | 19/01/2023 | 28/12/2025 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 707.21 | 262.57 | 37.13 | 38
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC | SM/12273 | Augmentation | Acceptance cum work order for Restoration of roads under different water supply schemes of Basirhat I Block under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001036/2024-2025 | 3626/BD | 20/12/2024 | 18/06/2025 | NISHITH BANERJEE | 45.36 | 0 | 0 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC | SM/12273 | Augmentation | Acceptance cum work order for Special repair and renovation of existing structures like Pump House, Boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Itinda Panitor, Joypur Gopmahal, Kachua Swarupnagar, Mathurapur, Mirzanagar, Nalkora, Paikardanga, Pifa and Gobindapur Water Supply Scheme of different block under Basirhat Sub-Division within Barasat Division, P.H.E Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 2474/BD | 17/07/2025 | 14/12/2025 | SAHA CONSTRUCTION & CO | 91.3 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC | SM/12273 | Augmentation | Restoration work of proposed laying along the existing road laying of pipe line for jal jeevan mission by PHE Department Govt. of west Bengal at GACHA from 0.00KM TO 1.432 KM of Gacha BOP Road under Barasat Division ,P.w Dte. |  |  | BILL/01622/2024-2025 | BP-2024-25-479 | 28/01/2025 | 28/01/2025 | EXECUTIVE ENGINEER-I, P.W.D., BARASAT DIVN | 29.34 | 0 | 0 | 0
Total | [13 empty] | 1313.48 | 267.41 | 20.36