## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC | SM/12274 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000172/2022-2023 | 491/BD | 17/02/2023 | 17/02/2023 | Resource Division | 184.92 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC | SM/12274 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000186/2022-2023 | 608/BD | 23/02/2023 | 23/02/2023 | Resource Division | 40.91 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC | SM/12274 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000145/2023-2024 | 4410/BD | 10/11/2023 | 10/11/2023 | Resource Division | 12.32 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC | SM/12274 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. II and III (Rep.) under Dhanyakuria W/S Scheme District of 24 Pgs. (N) 2022_PHED_426715_22 (N.I.E.T No. 26 of EE / EMD of 2022-2023) |  |  | ORD/001877/2023-2024 | 6726/EMD | 28/11/2023 | 28/12/2023 | S.S.ENTERPRISES | 26.67 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC | SM/12274 | Augmentation | Special Repairing of DI pipe, Supply of Sluice valve & construction of Sluice valve chamber for Augmentation of Dhanyakuria Water Supply Scheme in Basirhat-II block of North 24 Parganas district under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000080/2024-2025 | 935/BHTSD | 24/05/2024 | 31/05/2024 | ANKUSH CONSTRUCTION & CO. | 0.88 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC | SM/12274 | Augmentation | Special Repairing of existing HDPE & UPVC pipelines for Augmentation of Dhanyakuria Water Supply Scheme in Basirhat-II block of North 24 Parganas district under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000081/2024-2025 | 936/BHTSD | 24/05/2024 | 31/05/2024 | ANKUSH CONSTRUCTION & CO. | 0.98 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC | SM/12274 | Augmentation | Hiring additional Diesel Luxury Car on daily basis for the office use of the Assistant Engineer, Basirhat Sub-Division P.H.E. Dte. (Period: 01.07.2023 to 31.12.2023) | Assistant Engineer | Junior Engineer | ORD/002104/2023-2024 | 605/BHTSD | 28/06/2023 | 29/12/2023 | OM ENTERPRISE | 0.87 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC | SM/12274 | Augmentation | Continuation Work for Hiring additional Diesel Luxury Car on daily basis for the office use of the Assistant Engineer, Basirhat Sub-Division P.H.E. Dte. (Period: 01.01.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/002419/2023-2024 | 1291/BHTSD | 29/12/2023 | 29/06/2024 | OM ENTERPRISE | 0.86 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC | SM/12274 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2024-2025 | 3480/BD | 10/12/2024 | 10/12/2024 | Resource Division | 99.05 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC | SM/12274 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Dhanyakuria water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000745/2022-2023 | 3343/BD | 16/11/2022 | 03/08/2025 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 888.3 | 0 | 0 | 36
11 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC | SM/12274 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC | SM/12274 | Augmentation | Hiring of Diesel Luxury Car is essential for proper supervision of huge number of ground water based Augmentation Scheme at different blocks under Basirhat Sub-Division P.H.E. Dte. (Period 01.07.2024 to 31.12.2024 for Six Month), Sl.No. - 01 | Assistant Engineer | Junior Engineer | ORD/000157/2024-2025 | 1017/BHTSD | 28/06/2024 | 29/12/2024 | OM ENTERPRISE | 0.87 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC | SM/12274 | Augmentation | Acceptance cum work order for Eucalyptus Bullah Pilling for Emergency protection Work of Pipe line at different places for Augmentation of Dhanyakuria Water Supply Scheme of Basirhat Sub Division under Barasat Division P.H.E. | Assistant Engineer |  | ORD/001561/2024-2025 | 542/BD | 19/02/2025 | 21/03/2025 | SAMIR KUMAR DEY. | 52.24 | 0 | 0 | 0
Total | [13 empty] | 22648.65 | 0 | 0