## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC | SM/12275 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000249/2022-2023 | 933/BD | 22/03/2023 | 22/03/2023 | Resource Division | 120.6 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC | SM/12275 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line and Providing Functional Household Tap Connection for the leftout portion with protection work in connection with Augmentation of Durgapur Baylani water supply scheme (Z-I & II), Hingalganj Block of Hasnabad Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000100/2024-2025 | 2401/BD | 22/08/2024 | 17/08/2025 | M/S S.C. CIVIL ENTERPRISES | 116 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC | SM/12275 | Augmentation | Acceptance cum work order for Land development at OHR site in connection with augmentation of Durgapur Baylani w/s scheme (Z-I), Hingalganj under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000255/2025-2026 | 2334/BD | 07/07/2025 | 05/09/2025 | BABUSONA CONSTRUCTION. | 7.13 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC | SM/12275 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Durgapur Baylani Z-I w/s scheme, Hingalganj block under Hasnabad Sub-Division P.H.E. Dte.Part-C | Assistant Engineer | Junior Engineer | ORD/001467/2024-2025 | 342/HSD | 06/02/2025 | 16/02/2025 | M/S RAJPATH CONSTRUCTION. | 0.85 | 0 | 0 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC | SM/12275 | Augmentation | Acceptance cum work order for Laying of 140 mm(Near Asharia Paschim) ,180 mm(Near OHR) dia UPVC distribution pipe line in connection with Augmentation of Durgapur Baylani water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001534/2024-2025 | 389/HSD | 10/02/2025 | 20/02/2025 | M/S K.B.ENTERPRISE. | 0.86 | 0 | 0 | 100
Total | [13 empty] | 245.44 | 0 | 0