## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC | SM/12276 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Bansghata Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002790/2021-2022 | 142/BON | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 100 | 1
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC | SM/12276 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Replacement) under Bansghata W/S Scheme, District of 24 Pgs. (N). NIET No.- 26 of EE/EMD of 2022-23 (Sl. No.- 02) |  |  | ORD/000010/2023-2024 | 1552/EMD | 20/04/2023 | 20/05/2023 | TALUKDER & CO. | 21.41 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC | SM/12276 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 1246/BD | 25/04/2023 | 25/04/2023 | Resource Division | 113.03 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC | SM/12276 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000094/2023-2024 | 1864/BD | 23/06/2023 | 23/06/2023 | Resource Division | 31.18 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC | SM/12276 | Augmentation | Formal work order for Laying of Di rising main, DI/UPVC distribution pipe line and Providing (FHTC) for augmentation of Bansghata Water Supply Scheme, Bagdah Block, under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001171/2022-2023 | 760/BD | 10/03/2023 | 08/06/2023 | UMWELT ENGINEER PVT.LTD. | 747.85 | 747.34 | 99.93 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC | SM/12276 | Augmentation | Acceptance cum work order for Construction of Boundary wall, Approach Road, Earth Filling and Construction of 3.60 mtr. X 3.00 mtr. size Guard Room with sanitary and water supply arrangement incl. plinth protection at OHR site of Basghata Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000353/2024-2025 | 2358/BD | 20/08/2024 | 14/10/2025 | MD.SALIM GAZI. | 25.84 | 0 | 0 | 75
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC | SM/12276 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Replacement) under Bansghata W/S Scheme, District of 24 Pgs. (N). | Assistant Engineer | Junior Engineer | ORD/001133/2023-2024 | 4725/EMD | 04/08/2023 | 01/04/2025 | TALUKDER & CO. | 21.41 | 19.5 | 91.1 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC | SM/12276 | Augmentation | Acceptance cum work order for Sinking of 2 (two) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer at Augmentation of Bansghata Water Supply Scheme (H/W Site & 2nd T/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001156/2023-2024 | 518/BD | 20/02/2024 | 16/12/2024 | M/S N.K. BUILDERS | 30.51 | 6.1 | 20.01 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC | SM/12276 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at 1st Tube Well & 2nd Tube Well site and Construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Bansghata water Supply scheme, Bagdah Block within jurisdiction of Bongaon Sub-Division, under Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001500/2023-2024 | 4471/BD | 22/11/2023 | 09/01/2025 | ROY CHOWDHURY CONSTRUCTION. | 12.67 | 9.13 | 72.06 | 73
Total | [13 empty] | 1008.73 | 786.92 | 78.01