## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC | SM/12278 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Sahebkhali water supply scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000938/2022-2023 | 88/BD | 11/01/2023 | 11/04/2023 | M/S NIRMAN CONSTRUCTION. | 354.45 | 323.2 | 91.18 | 1
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC | SM/12278 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. VI (New) under Sahebkhali W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001286/2023-2024 | 4940/EMD | 18/08/2023 | 17/09/2023 | KUNDU ELECTRICAL ENTERPRISE | 13.82 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC | SM/12278 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000258/2022-2023 | 920/BD | 22/03/2023 | 22/03/2023 | Resource Division | 137.48 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC | SM/12278 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000120/2023-2024 | 4175/BD | 30/10/2023 | 30/10/2023 | Resource Division | 18.56 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC | SM/12278 | Augmentation | Formal work order for construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Sahebkhali water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001266/2023-2024 | 4200/BD | 31/10/2023 | 30/10/2024 | M/S RAJPATH CONSTRUCTION. | 150.42 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC | SM/12278 | Augmentation | Acceptance cum work order for Sinking of 1 Nos. 330.00 mtr. Deep 100 X 50 mm. dia. Trial-cum-production Tube well fitted with Indian Mark - II pump with PVC pipe & strainers at T/W site-1 for Sahebkhali w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. |  |  | ORD/000022/2024-2025 | 629/HSD | 12/06/2024 | 22/06/2024 | DEB PRASAD GHOSH. | 3.5 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC | SM/12278 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No -I with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Sahebkhali w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000534/2024-2025 | 2900/BD | 03/10/2024 | 02/11/2024 | SUBHAJIT SAHA | 31.68 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC | SM/12278 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Replacement) under Sahebkhali W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001277/2023-2024 | 4938/MD | 18/08/2023 | 17/09/2023 | KARTICK BAL | 41.4 | 36.57 | 88.34 | 70
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC | SM/12278 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Sahebkhali w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001683/2023-2024 | 526/BD | 20/02/2024 | 05/04/2024 | UTPAL CONSTRUCTION & CO. | 61.24 | 48.73 | 79.58 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC | SM/12278 | Augmentation | Acceptance cum work order for Sinking of 3 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3, 4 & 5 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Sahebkhali w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001932/2023-2024 | 915/BD | 15/03/2024 | 14/05/2024 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 94.87 | 71.18 | 75.03 | 100
11 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC | SM/12278 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.IV and V (Replacement) under Sahebkhali W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001278/2023-2024 | 4939/EMD | 18/08/2023 | 01/05/2025 | ASHOKE ADHIKARY | 27.57 | 0 | 0 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC | SM/12278 | Augmentation | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) for Augmentation of Sahebkhali w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001293/2024-2025 | 301/BD | 28/01/2025 | 13/04/2025 | M/S S.HAQUE & CO. | 12.36 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC | SM/12278 | Augmentation | Formal work order for Additional laying of UPVC distribution pipe line including protection work for DI pipe at N/H/O Provas Halder towards Suvomay Mondal house & other allied work for UPVC pipe laying at different places in connection with Augmentation of Sahebkhali w/s scheme (Z-I), Hingalganj block within Hasnabad Sub-Division under Barasat Division P.H.E. Dte. | Assistant Engineer |  | ORD/000069/2025-2026 | 1797/BD | 30/05/2025 | 29/07/2025 | SAHA CONSTRUCTION & CO | 139.89 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC | SM/12278 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Sahebkhali water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000031/2023-2024 | 1304/BD | 26/04/2023 | 11/06/2025 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 554.49 | 492.32 | 88.79 | 90
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC | SM/12278 | Augmentation | Formal work order for Construction of 250 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Sahebkhali water supply scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001228/2023-2024 | 4110/BD | 17/10/2023 | 16/12/2025 | ROY CHOWDHURY CONSTRUCTION. | 140.37 | 91.08 | 64.89 | 75
16 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC | SM/12278 | Augmentation | Formal work order for Laying of DI rising main in connection with Augmentation of Sahebkhali water supply scheme (Z-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000099/2024-2025 | 2098/BD | 26/07/2024 | 24/10/2024 | ABDUL ALIM MONDAL. | 104.06 | 26.65 | 25.61 | 100
17 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC | SM/12278 | Augmentation | Acceptance cum work order for Land development at Head Work Site in connection with Augmentation of Sahebkhali w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000059/2025-2026 | 1609/BD | 19/05/2025 | 03/06/2025 | SARKAR ENTERPRISE & CO. | 9.64 | 0 | 0 | 100
18 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC | SM/12278 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Sahebkhali water supply scheme (Z-I) , Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001304/2024-2025 | 150/HSD | 27/01/2025 | 06/02/2025 | M/S DATTA ENTERPRISE. | 0.95 | 0 | 0 | 100
Total | [13 empty] | 1896.74 | 1089.75 | 57.45