## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC | SM/12377 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Nalabara Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002751/2021-2022 | 454/ BHTSD | 23/03/2022 | 07/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.97 | 4.97 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC | SM/12377 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Nalabara Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002752/2021-2022 | 455/ BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.61 | 3.61 | 100 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC | SM/12377 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. big dia. 300 mtr deep tubewell by D.R. Rig method using PVC pipe & strainer having 300 mm dia. 36 mtr. long filter for Augmentation of Nalabara Zone-II water supply scheme in Swarupnagar Block of Basirhat Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000980/2023-2024 | 2800/BD | 12/09/2023 | 12/10/2023 | DHELA BABA ENTERPRISE | 21.53 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC | SM/12377 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 1260/BD | 25/04/2023 | 25/04/2023 | Resource Division | 381.58 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC | SM/12377 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000067/2023-2024 | 1629/BD | 01/06/2023 | 01/06/2023 | Resource Division | 71.08 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC | SM/12377 | Augmentation | Formal work order for Laying of DI / UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection) by Augmentation of Nalabara (Zone-I) Water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000776/2023-2024 | 2713/BD | 05/09/2023 | 04/03/2025 | GARGO TRADERS | 559.43 | 403.19 | 72.07 | 72
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC | SM/12377 | Augmentation | Regarding Restoration charges for road damages. |  |  | BILL/03465/2023-2024 | BP-2023-24-830 | 15/03/2024 | 15/03/2024 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 49.56 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC | SM/12377 | Augmentation | Regarding Restoration charges for road damages. |  |  | BILL/03468/2023-2024 | BP-2023-24-830 | 15/03/2024 | 15/03/2024 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 32.73 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC | SM/12377 | Augmentation | New service connection at P.H.No- II of Nalabora water supply scheme under EMSD-I ,PHE Dte .im24Pgs(N). |  |  | BILL/04867/2023-2024 | BP-322-23-24 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 16.96 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC | SM/12377 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II, III and IV (Rep.) under Nalabara W/S Scheme and Pump House No-I and II under Barabankra W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001161/2023-2024 | 4811/EMD | 09/08/2023 | 01/06/2025 | M/S. SAJAHAN CHOWDHURY | 78.21 | 14.77 | 18.88 | 46
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC | SM/12377 | Augmentation | Acceptance cum work order for Balance Work of Laying of UPVC Distribution pipe line and providing FHTC for augmentation of Nalabara Z-II water Supply Scheme within Swarupnagar Block under Basirhat Sub Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001537/2024-2025 | 399/BD | 05/02/2025 | 31/01/2026 | H.I.ENTERPRISE. | 75.98 | 0 | 0 | 65
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC | SM/12377 | Augmentation | Formal work order for Laying of UPVC distribution pipeline and Providing FHTC (Functional Household Tap Connection) for Augmentation of Nalabara Zone-II Water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000005/2023-2024 | 1125/BD | 11/04/2023 | 30/06/2025 | H.I.ENTERPRISE. | 634.74 | 613.98 | 96.73 | 60
Total | [13 empty] | 1930.39 | 1040.52 | 53.9