## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Additional Survey work for DPR Preparation for DAKSHIN CHATRA ZONE -1 Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001980/2021-2022 | 352/BHTSD | 14/03/2022 | 29/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.38 | 1.36 | 98.73 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Hiring Diesel Luxury Car on daily basis (for 06 months from 01.01.2023 to 30.06.2023) for the office use of the Assistant Engineer, Basirhat Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001343/2022-2023 | 1420 /BHTSD | 30/12/2022 | 29/06/2023 | OM ENTERPRISE | 0.86 | 2.33 | 271.36 | 100
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Route Survey, Design Drawing & DPR Preparation for DAKSHIN CHATRA ZONE -1 Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001979/2021-2022 | 351/BHTSD | 14/03/2022 | 29/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.95 | 4.95 | 100 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Dakshin Chatra Zone-I water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000023/2023-2024 | 1210/BD | 20/04/2023 | 24/02/2026 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 971.71 | 571.4 | 58.8 | 38
5 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 25.6 | 0.12 | 11
6 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No II (Rep.) (Zone-I and II) under Dakshin Chatra W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001911/2023-2024 | 6734/EMD | 29/11/2023 | 29/12/2023 | CONCORD ENGINEERING | 26.08 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Continuation Work for Hiring Diesel Luxury Car on daily basis for the office use of the Assistant Engineer, Basirhat Sub-Division P.H.E. Dte. (Period: 01.01.2024 to 30.06.2024 for Six Month) | Assistant Engineer | Junior Engineer | ORD/002197/2023-2024 | 1290/BHTSD | 29/12/2023 | 28/06/2024 | DEB KUMAR DAS. | 0.86 | 1.51 | 174.74 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 1254/BD | 25/04/2023 | 25/04/2023 | Resource Division | 260.28 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 1632/BD | 01/06/2023 | 01/06/2023 | Resource Division | 48.44 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Laying of HDPE pipe line and Repairing of DI pipelines including supply of Sluice valve (200 mm) for interconnection of AIRP under Augmentation work of Dakshin Chatra Zone-I Water Supply Scheme under Basirhat Sub Division , P.H.E. Dte. under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000079/2024-2025 | 929/BHTSD | 24/05/2024 | 31/05/2024 | S.R.M. ENTERPRISE. | 1 | 1 | 100 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Supply of Sluice valve (200 mm) including construction of Sluice valve chamber for Augmentation of Dakshin Chatra Zone-I Water Supply Scheme under Basirhat Sub Division , P.H.E. Dte. under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000075/2024-2025 | 928/BHTSD | 24/05/2024 | 31/05/2024 | ROHAN MONDAL. | 0.97 | 0.97 | 100 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Road Restoration work |  |  | BILL/00857/2024-2025 | BP-2024-25-277 | 17/09/2024 | 17/09/2024 | EXECUTIVE ENGINEER-II, P.W.D,BARASAT DIVN | 76.63 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Restoration for damages made of black top portion due to laying of 350 mm dia pipe line by PHE dte. under Jal Jeevan Mission at 4.00 kmp (Dakterkhnar more) Tentulia- Maslandpur Road under Barasat Division, PWD during the year 2024-2025. |  |  | BILL/00502/2025-2026 |  | 20/06/2025 | 20/06/2025 | EXECUTIVE ENGINEER-II, P.W.D,BARASAT DIVN | 2.91 | 0 | 0 | 0
Total | [13 empty] | 22735.81 | 609.12 | 2.68