## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Bachhra piped Water supply scheme | SM/12712 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (BACHHRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002701/2021-2022 | 244/HSD | 03/02/2022 | 18/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.8 | 4.8 | 100 | 1
2 | NORTH 24 PARGANAS | Minakhan | Central Drilling | Bachhra piped Water supply scheme | SM/12712 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Bachhra piped Water supply scheme | SM/12712 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 100 cum capacity CWR, pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Bachhra w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000115/2023-2024 | 1690/BD | 07/06/2023 | 07/06/2024 | R.K.MANDAL & CO. | 267.07 | 223.92 | 83.84 | 85
4 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Bachhra piped Water supply scheme | SM/12712 | New | Material Requisition To Resource Division |  |  | RTOR000221/2022-2023 | 876/BD | 22/03/2023 | 22/03/2023 | Resource Division | 30.63 | 0 | 0 | 0
5 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Bachhra piped Water supply scheme | SM/12712 | New | Quotation for Service Connection Charges for PH- II under Bachra W/S Scheme in the district of North 24 Pgs. |  |  | BILL/05546/2023-2024 | BP-351-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.14 | 0 | 0 | 0
6 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Bachhra piped Water supply scheme | SM/12712 | New | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection within Bachra water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. |  |  | ORD/001905/2024-2025 | 541/HSD | 10/03/2025 | 20/03/2025 | M/S SOURAV DAS | 0.72 | 0 | 0 | 0
7 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Bachhra piped Water supply scheme | SM/12712 | New | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection within Bachra water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. |  |  | ORD/000267/2025-2026 | 1477/HSD | 14/07/2025 | 24/07/2025 | M/S SOURAV DAS | 0.72 | 0 | 0 | 0
8 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Bachhra piped Water supply scheme | SM/12712 | New | Supplementary Quotation for Additional Work at PH-I under Bachra W/S schemen under Haroa CCC. |  |  | BILL/02719/2024-2025 | BP-294 | 27/03/2025 | 27/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.77 | 0 | 0 | 0
9 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Bachhra piped Water supply scheme | SM/12712 | New | Quotation for 11 KV LT Bulk Connection at PH-I of Bachra W/S scheme |  |  | BILL/02399/2024-2025 | BP-214 | 09/01/2025 | 09/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.49 | 0 | 0 | 0
Total | [13 empty] | 21656.11 | 228.72 | 1.06