## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Phulbari Abad Piped Water Supply Scheme. | SM/12717 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (PHULBARI ABAD Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002730/2021-2022 | 306/HSD | 15/02/2022 | 02/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.82 | 0 | 0 | 1
2 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Phulbari Abad Piped Water Supply Scheme. | SM/12717 | New | Material Requisition To Resource Division |  |  | RTOR000218/2022-2023 | 886/BD | 22/03/2023 | 22/03/2023 | Resource Division | 11.94 | 0 | 0 | 0
3 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Phulbari Abad Piped Water Supply Scheme. | SM/12717 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 150 cum capacity CWR , pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Phulbari Abad w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000117/2023-2024 | 1691/BD | 07/06/2023 | 07/06/2024 | M/S B.K.ENTERPRISE. | 252.21 | 0 | 0 | 80
4 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Phulbari Abad Piped Water Supply Scheme. | SM/12717 | New | Quotation for Service Connection Charges for PH- I under Fulbari Abad W/S Scheme in the district of North 24 Pgs. |  |  | BILL/04869/2023-2024 | BP-326-23-24 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.66 | 0 | 0 | 0
5 | NORTH 24 PARGANAS | Minakhan | Central Drilling | Phulbari Abad Piped Water Supply Scheme. | SM/12717 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21615.4 | 0 | 0