## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Ghipukuria Piped Water Supply Scheme. | SM/12718 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (GHIPUKURIA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002990/2021-2022 | 275/HSD | 09/02/2022 | 24/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.83 | 0 | 0 | 1
2 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Ghipukuria Piped Water Supply Scheme. | SM/12718 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (GHIPUKURIA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002711/2021-2022 | 274/HSD | 09/02/2022 | 24/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
3 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Ghipukuria Piped Water Supply Scheme. | SM/12718 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (GHIPUKURIA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002712/2021-2022 | 275/HSD | 09/02/2022 | 24/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.83 | 0.83 | 100 | 1
4 | NORTH 24 PARGANAS | Minakhan | Central Drilling | Ghipukuria Piped Water Supply Scheme. | SM/12718 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 24.06 | 0.11 | 11
5 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Ghipukuria Piped Water Supply Scheme. | SM/12718 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 150 cum capacity CWR , pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Ghipukuria w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000144/2023-2024 | 1698/BD | 08/06/2023 | 08/06/2026 | TIRUPATI ENTERPRISES | 270.61 | 111.74 | 41.29 | 70
6 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Ghipukuria Piped Water Supply Scheme. | SM/12718 | New | Material Requisition To Resource Division |  |  | RTOR000211/2022-2023 | 891/BD | 22/03/2023 | 22/03/2023 | Resource Division | 15.9 | 0 | 0 | 0
7 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Ghipukuria Piped Water Supply Scheme. | SM/12718 | New | Quotation for New LT service Connection charges for PH-II under Ghipukuria W/s scheme |  |  | BILL/03032/2024-2025 | BP-301 | 27/03/2025 | 27/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.19 | 0 | 0 | 0
8 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Ghipukuria Piped Water Supply Scheme. | SM/12718 | New | Quotation for New LT service Connection at PH-I under Ghipukuria W/S scheme |  |  | BILL/03033/2024-2025 | BP-302 | 27/03/2025 | 27/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 13.04 | 0 | 0 | 0
Total | [13 empty] | 21649.99 | 141.45 | 0.65