## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Jhikra Piped Water Supply Scheme. | SM/12719 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (JHIKRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002716/2021-2022 | 279/HSD | 09/02/2022 | 24/02/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 1.46 | 0 | 0 | 1
2 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Jhikra Piped Water Supply Scheme. | SM/12719 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (JHIKRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002996/2021-2022 | 279/HSD | 09/02/2022 | 24/02/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 1.46 | 0 | 0 | 1
3 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Jhikra Piped Water Supply Scheme. | SM/12719 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (JHIKRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002997/2021-2022 | 278/HSD | 09/02/2022 | 24/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 0 | 0 | 1
4 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Jhikra Piped Water Supply Scheme. | SM/12719 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (New) under Jhikra W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001129/2023-2024 | 4721/EMD | 04/08/2023 | 03/09/2023 | DEY ENTERPRISE | 21.13 | 0 | 0 | 0
5 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Jhikra Piped Water Supply Scheme. | SM/12719 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (JHIKRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002715/2021-2022 | 278/HSD | 09/02/2022 | 24/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 0 | 0 | 1
6 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Jhikra Piped Water Supply Scheme. | SM/12719 | New | Material Requisition To Resource Division |  |  | RTOR000220/2022-2023 | 873/BD | 22/03/2023 | 22/03/2023 | Resource Division | 17.57 | 0 | 0 | 0
7 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Jhikra Piped Water Supply Scheme. | SM/12719 | New | Acceptance cum work order for Construction of RCC culvert, cut-off wall, approach road and other allied works at Over Head Reservoir site (HW site) for Jhikra w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001814/2023-2024 | 677/BD | 01/03/2024 | 15/03/2024 | NURJAHAN ENTERPRISE. | 8.5 | 0 | 0 | 86
8 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Jhikra Piped Water Supply Scheme. | SM/12719 | New | Acceptance cum work order for Construction of RCC culvert, cut-off wall, approach road and other allied works at Kalil Khal N/H/O Rajjack Molla (Between node point 101 to 294) for Jhikra w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000009/2024-2025 | 1528/BD | 07/06/2024 | 05/03/2025 | RUDRA DAS. | 9.89 | 0 | 0 | 85
9 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Jhikra Piped Water Supply Scheme. | SM/12719 | New | Acceptance cum work order for Protection works for protection of newly laid UPVC distribution pipe line at near Jhikra Radhagobinda Mandir at Jhikra Purba para within Jhikra w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000989/2024-2025 | 3465/BD | 09/12/2024 | 08/01/2025 | STAR CONSTRUCTION. | 9.41 | 0 | 0 | 0
10 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Jhikra Piped Water Supply Scheme. | SM/12719 | New | Acceptance cum work order for Protection works for protection of newly laid UPVC distribution pipe line at N/H/O Utpal Mondal at Jhikra Paschim para within Jhikra w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E.Dte. | Assistant Engineer |  | ORD/000991/2024-2025 | 3676/BD | 24/12/2024 | 23/01/2025 | A. M. ENTERPRISE (BASIRHAT) | 9.06 | 0 | 0 | 0
11 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Jhikra Piped Water Supply Scheme. | SM/12719 | New | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site within Jhikra W/S scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 879/HSD | 07/08/2024 | 17/08/2024 | M/S NIRMAN CONSTRUCTION. | 0.75 | 0 | 0 | 100
12 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Jhikra Piped Water Supply Scheme. | SM/12719 | New | Quotation for Service Connection Charges for PH- I under Jhikra W/S Scheme in the district of North 24 Pgs. |  |  | BILL/05547/2023-2024 | BP-352-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.54 | 0 | 0 | 0
13 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Jhikra Piped Water Supply Scheme. | SM/12719 | New | Service connection charges at PH-I under Jhikra W/S Scheme |  |  | BILL/04757/2023-2024 | BP-296-23-24 | 28/02/2024 | 28/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.71 | 0 | 0 | 0
14 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Jhikra Piped Water Supply Scheme. | SM/12719 | New | New service connection at P.H.No- I of Jhikra water supply scheme under EMSD-I ,PHE Dte .im24Pgs(N). |  |  | BILL/04760/2023-2024 | BP-299-23-24 | 28/02/2024 | 28/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.53 | 0 | 0 | 0
15 | NORTH 24 PARGANAS | Minakhan | Central Drilling | Jhikra Piped Water Supply Scheme. | SM/12719 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
16 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Jhikra Piped Water Supply Scheme. | SM/12719 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Jhikra w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000138/2023-2024 | 1704/BD | 08/06/2023 | 29/05/2026 | M/S NIRMAN CONSTRUCTION. | 403.64 | 0 | 0 | 80
17 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Jhikra Piped Water Supply Scheme. | SM/12719 | New | Acceptance cum work order for Protection works for protection of newly laid UPVC distribution pipe line at N/H/O Pankaj Mondal at Jhikra Majher para within Jhikra w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000988/2024-2025 | 3642/BD | 23/12/2024 | 22/04/2025 | GAZI ENTERPRISE | 9.32 | 0 | 0 | 100
18 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Jhikra Piped Water Supply Scheme. | SM/12719 | New | Acceptance cum work order for Construction of boundary wall with column structure at Head Work site (PH No-1) & PH No- 2 within Jhikra w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/002264/2024-2025 | 1027/BD | 28/03/2025 | 26/06/2025 | M/S NIRMAN CONSTRUCTION. | 31.11 | 0 | 0 | 0
Total | [13 empty] | 21889.51 | 0 | 0