## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Tapla Kusangra Piped Water Supply Scheme. | SM/12720 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (TAPLA KUSANGRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002734/2021-2022 | 310/HSD | 15/02/2022 | 02/03/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 4.82 | 4.82 | 100 | 1
2 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Tapla Kusangra Piped Water Supply Scheme. | SM/12720 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (TAPLA KUSANGRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002735/2021-2022 | 311/HSD | 15/02/2022 | 02/03/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 0.52 | 0.52 | 100 | 1
3 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Tapla Kusangra Piped Water Supply Scheme. | SM/12720 | New | Material Requisition To Resource Division |  |  | RTOR000219/2022-2023 | 887/BD | 22/03/2023 | 22/03/2023 | Resource Division | 12.08 | 0 | 0 | 0
4 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Tapla Kusangra Piped Water Supply Scheme. | SM/12720 | New | Service connection charges at PH-I under Tapla Kusangra W/S Scheme |  |  | BILL/04753/2023-2024 | BP-289-23-24 | 27/02/2024 | 27/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.21 | 0 | 0 | 0
5 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Tapla Kusangra Piped Water Supply Scheme. | SM/12720 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Tapla Kusangra w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000122/2023-2024 | 1682/BD | 07/06/2023 | 01/04/2026 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 328.77 | 222.42 | 67.65 | 80
6 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Tapla Kusangra Piped Water Supply Scheme. | SM/12720 | New | Acceptance cum work order for Construction of boundary wall with column structure at Head Work site within Tapla Kusangra w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/002263/2024-2025 | 1031/BD | 28/03/2025 | 26/06/2025 | ACHARJEE AND ASSOCIATES | 17.53 | 0 | 0 | 0
Total | [13 empty] | 373.94 | 227.77 | 60.91