## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. | SM/12735 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Khulna Bhanderkhali W/S scheme (Zone-I), Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000683/2022-2023 | 3182/BD | 01/11/2022 | 30/01/2023 | UMWELT ENGINEER PVT.LTD. | 497.55 | 485.08 | 97.49 | 100
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. | SM/12735 | Augmentation | Formal work order for construction of 450 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Khulna Bhanderkhali water supply scheme (Zone - I), Sandeshkhali-II Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000753/2023-2024 | 2610/BD | 29/08/2023 | 28/08/2026 | M/S PROGATI ENTERPRISE. | 194.78 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. | SM/12735 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Khulna Bhanderkhali w/s scheme (Z-I), Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001173/2022-2023 | 786/BD | 13/03/2023 | 12/04/2023 | MONDAL & CO. (BASIRHAT). | 47.09 | 37.47 | 79.57 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. | SM/12735 | Augmentation | Acceptance cum work order for Repairing of Pump House at PH No- 1, 2 & 3 for Khulna Bhandarkhali w/s scheme (Zone-I), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000908/2023-2024 | 2719/BD | 05/09/2023 | 26/09/2023 | LAHIRI CONSTRUCTION. | 6.11 | 6.01 | 98.46 | 80
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. | SM/12735 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no-1 in connection with Augmentation of Khulna Bhandarkhali w/s scheme (Z-I), Sandeshkhali -II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000272/2023-2024 | 799/HSD | 13/07/2023 | 23/07/2023 | JESMINE ENTERPRISE. | 0.9 | 0.88 | 97.73 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. | SM/12735 | Augmentation | Acceptance cum work order for Construction of approach road with cement concrete at Pump house No-1 within Khulna Bhanderkhali w/s scheme (Z-I), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000274/2023-2024 | 801/HSD | 13/07/2023 | 20/07/2023 | JESMINE ENTERPRISE. | 0.57 | 0.51 | 89.33 | 100
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. | SM/12735 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Zone-I)(Rep.) under Khulna-Bhanderkhali W/S Scheme District of 24 Pgs. (N) NIET No.- 26 of EE/EMD of 2022-23 (Sl. No.- 29) | Assistant Engineer | Junior Engineer | ORD/001906/2022-2023 | 1170/EMD | 21/03/2023 | 20/04/2023 | M.S. ENTERPRISE | 39.16 | 35.99 | 91.92 | 90
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. | SM/12735 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.-2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Khulna Bhanderkhali w/s scheme (Z-I), Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000736/2023-2024 | 2490/BD | 18/08/2023 | 17/09/2023 | M/S DATTA ENTERPRISE. | 26.91 | 21.67 | 80.54 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. | SM/12735 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Khulna Bhanderkhali water supply scheme (Z-I) , Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001295/2023-2024 | 1417/HSD | 06/11/2023 | 13/11/2023 | ANKUSH CONSTRUCTION & CO. | 0.98 | 0.96 | 97.96 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. | SM/12735 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no-3 in connection with Augmentation of Khulna Bhandarkhali w/s scheme (Z-I), Sandeshkhali -II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002346/2023-2024 | 800/HSD | 24/05/2023 | 03/06/2023 | JESMINE ENTERPRISE. | 0.84 | 0.8 | 95.39 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. | SM/12735 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000256/2022-2023 | 923/BD | 22/03/2023 | 22/03/2023 | Resource Division | 94.23 | 0 | 0 | 0
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. | SM/12735 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-3 in connection with Augmentation for Khulna Bhanderkhali water supply scheme (Z-I) , Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001913/2023-2024 | 285/HSD | 06/03/2024 | 16/03/2024 | DEB PRASAD GHOSH. | 0.67 | 0.67 | 99.38 | 100
13 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. | SM/12735 | Augmentation | Quotation for Service Connection Charges for PH- I under Bhanderkhali W/S Scheme in the district of North 24 Pgs. JL No- 92, Plot No-1 & 65/264 |  |  | BILL/04871/2023-2024 | BP-320-23-24 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.55 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. | SM/12735 | Augmentation | Enhancement of GST for the work providing FHTC for augmentation of Khulna Bhanderkhali (Zone-I) |  |  | BILL/00273/2024-2025 | BP-2024-25-78 | 10/07/2024 | 10/07/2024 | UMWELT ENGINEER PVT.LTD. | 25.4 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. | SM/12735 | Augmentation | Quotation for Service Connection Charges for PH- II under Bhanderkhali W/S Scheme in the district of North 24 Pgs. JL No- 92, Plot No- 63 |  |  | BILL/04872/2023-2024 | BP-327-23-24 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 18.31 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. | SM/12735 | Augmentation | Quotation for Service Connection Charges for PH- III under Bhanderkhali W/S Scheme in the district of North 24 Pgs. JL No. 92, Plot No-112. |  |  | BILL/04870/2023-2024 |  | 04/03/2024 | 04/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.02 | 0 | 0 | 0
17 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. | SM/12735 | Augmentation | Acceptance cum work order for Providing Functional Household tap connection at Sitalia FP School, South Hatgacha Jr. High School, Dakshin Hatgacha Adibasi SSK and Uttar Hatgacha SSK within the command area of Khulna Bhanderkhaliw/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. |  |  | ORD/001909/2024-2025 | 543/HSD | 10/03/2025 | 20/03/2025 | M/S RAJPATH CONSTRUCTION. | 0.83 | 0 | 0 | 0
18 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. | SM/12735 | Augmentation | Acceptance cum work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Khulna Bhanderkhali w/s scheme (Z-I), Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001402/2024-2025 | 392/BD | 05/02/2025 | 06/04/2025 | ANKUSH CONSTRUCTION & CO. | 12.47 | 0 | 0 | 100
Total | [13 empty] | 981.35 | 590.04 | 60.13