## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-II to accommodate FHTC | SM/12895 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Bithari Z-II Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/002966/2021-2022 | 452/BHT | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.75 | 4.75 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-II to accommodate FHTC | SM/12895 | Augmentation | Additional Survey work for DPR Preparation for BITHARI ZONE -2 Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002967/2021-2022 | 453/BHT | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.63 | 0.63 | 100 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-II to accommodate FHTC | SM/12895 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. big dia. 330 mtr deep tubewell by D.R. Rig method using PVC pipe & strainer having 300 mm dia. 36 mtr. long filter for Augmentation of Bithari Zone-IIB water supply scheme in Baduria Block of Basirhat Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000977/2023-2024 | 2801/BD | 12/09/2023 | 12/10/2023 | DHELA BABA ENTERPRISE | 23.31 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-II to accommodate FHTC | SM/12895 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 1263/BD | 25/04/2023 | 25/04/2023 | Resource Division | 52.64 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-II to accommodate FHTC | SM/12895 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000142/2023-2024 | 4427/BD | 10/11/2023 | 10/11/2023 | Resource Division | 23.94 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-II to accommodate FHTC | SM/12895 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Bithari Zone-II A water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000136/2023-2024 | 1710/BD | 08/06/2023 | 26/02/2025 | UTPAL CONSTRUCTION & CO. | 234.15 | 177.81 | 75.94 | 50
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Bithari Zone-II to accommodate FHTC | SM/12895 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-II)(Rep.) under Bithari W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001134/2023-2024 | 4726/EMD | 04/08/2023 | 03/09/2023 | SINHA ELECTRICALS | 26.08 | 5.77 | 22.14 | 60
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-II to accommodate FHTC | SM/12895 | Augmentation | Regarding Restoration charges for road damages. |  |  | BILL/03471/2023-2024 | BP-2023-24-830 | 15/03/2024 | 15/03/2024 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 24.25 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-II to accommodate FHTC | SM/12895 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Bithari Z-II B water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000163/2023-2024 | 1719/BD | 08/06/2023 | 06/05/2025 | CHAKRABORTTI ENTERPRISE. | 180.55 | 144.91 | 80.26 | 20
Total | [13 empty] | 570.28 | 333.86 | 58.54