## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC | SM/13040 | Augmentation | Additional Survey work for DPR Preparation for ATURIA Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001977/2021-2022 | 349/BHTSD | 14/03/2022 | 29/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.98 | 1.91 | 96.83 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC | SM/13040 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ATURIA Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001976/2021-2022 | 348/BHTSD | 14/03/2022 | 29/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.97 | 4.97 | 100 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC | SM/13040 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Aturia Zone-II water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000032/2023-2024 | 1305/BD | 26/04/2023 | 16/01/2025 | JAL PRAVAHIKA PVT. LTD. | 282.82 | 143 | 50.56 | 31
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC | SM/13040 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Aturia (Zone-I) water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000130/2023-2024 | 1702/BD | 08/06/2023 | 31/10/2025 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 546.47 | 462.6 | 84.65 | 41
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC | SM/13040 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Rep.) under Shimla-Durgapur W/S Scheme and Aturia W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001164/2023-2024 | 4814/EMD | 09/08/2023 | 08/09/2023 | ORIENTAL ENGINEERING CO. | 78.18 | 0 | 0 | 30
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC | SM/13040 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. big dia. 300 mtr deep tubewell by D.R. Rig method using PVC pipe & strainer having 300 mm dia. 36 mtr. long filter for Augmentation of Aturia Zone-II water supply scheme in Baduria Block of Basirhat Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000999/2023-2024 | 2803/BD | 12/09/2023 | 12/10/2023 | SAHA CONSTRUCTION & CO | 21.53 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC | SM/13040 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 1253/BD | 25/04/2023 | 25/04/2023 | Resource Division | 86.25 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC | SM/13040 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000140/2023-2024 | 4409/BD | 10/11/2023 | 10/11/2023 | Resource Division | 42.27 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC | SM/13040 | Augmentation | Regarding Restoration charges for road damages. |  |  | BILL/03463/2023-2024 | BP-2023-24-830 | 15/03/2024 | 15/03/2024 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 48.02 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC | SM/13040 | Augmentation | Acceptance cum work order for Eucalyptus Bullah Pilling for Emergency protection Work of Pipe line at different places for Augmentation of Aturia Zone-I Water Supply Scheme of Basirhat Sub Division under Barasat Division P.H.E. | Assistant Engineer |  | ORD/001560/2024-2025 | 724/BD | 07/03/2025 | 06/04/2025 | SHIBU BISWAS. | 44.01 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC | SM/13040 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different villages of various PWSS of Baduria Block within the jurisdiction of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. (Part - B) | Assistant Engineer | Junior Engineer | ORD/001458/2024-2025 | 144/BHTSD | 29/01/2025 | 18/02/2025 | M.R.CONSTRUCTION. | 0.88 | 0 | 0 | 90
Total | [13 empty] | 1157.36 | 612.49 | 52.92