## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Supply, delivery & installation of 30HP Centrifugal pump motor set at High Lift of Padmapukuria W/S scheme under Eastern Mechanical Division, P.H.E, Dte. Dist. 24 Pgs. (N). NIET No.- 15 of EE/EMD of 2022-23 (Sl. No.- 16) |  |  | ORD/000126/2022-2023 | 6153/EMD | 11/11/2022 | 11/12/2022 | D.K. ELECTRIC | 7.88 | 7.88 | 100 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at N/H/O Rahaman Molla, Motaleb Molla at Maliari Sekh para & Other places for Augmentation of Padmapukuria w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000448/2022-2023 | 1196/HSD | 13/07/2022 | 23/07/2022 | M/S ATRI BISWAS | 2.05 | 2.05 | 99.89 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Padmapukuria water supply scheme (Zone-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000928/2022-2023 | 127/BD | 16/01/2023 | 16/04/2023 | MONDAL & CO. (BASIRHAT). | 416.99 | 369.68 | 88.66 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000176/2022-2023 | 518/BD | 20/02/2023 | 20/02/2023 | Resource Division | 124.37 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000263/2022-2023 | 913/BD | 22/03/2023 | 22/03/2023 | Resource Division | 48.74 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Padmapukuria water supply scheme (Zone-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001008/2022-2023 | 171/BD | 19/01/2023 | 19/04/2023 | M/S B.K.ENTERPRISE. | 446.28 | 357.95 | 80.21 | 75
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 150 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Padmapukuria w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000019/2023-2024 | 1205/BD | 20/04/2023 | 20/05/2023 | ABDUL ALIM MONDAL. | 25.87 | 23.75 | 91.8 | 63
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Acceptance cum work order for Construction of protection wall for protection of UPVC pipe line at Maliari Masjid pond for Augmentation of Padmapukuria w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001400/2023-2024 | 1494/HSD | 01/12/2023 | 16/12/2023 | BABUSONA CONSTRUCTION. | 4.41 | 4.41 | 99.99 | 68
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Acceptance cum work order for Construction of protection wall for protection of UPVC pipe line at N/H/O Hasmat Molla at Maliari for Augmentation of Padmapukuria w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001391/2023-2024 | 1495/HSD | 01/12/2023 | 16/12/2023 | GAZI ENTERPRISE | 4.03 | 3.94 | 97.81 | 70
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site within Padmapukuria W/S scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000579/2024-2025 | 1141/HSD | 24/09/2024 | 04/10/2024 | TRISHA ENTERPRISE & CO. | 0.87 | 0.87 | 100 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site within Padmapukuria W/S scheme (Z-II), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000581/2024-2025 | 1143/HSD | 24/09/2024 | 04/10/2024 | M/S R.B.S.ENTERPRISE. | 0.87 | 0 | 0 | 100
12 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | New Service Connection at PH-II under Minakhan W/S Scheme |  |  | BILL/04122/2023-2024 | BP-260-23-24 | 02/01/2024 | 02/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.25 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Formal work order for construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per Deptt. design, drawing and specification including bored pile with pile cap for Augmentaion of Padmapukuria water supply scheme (Zone - II), Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000241/2023-2024 | 1739/BD | 08/06/2023 | 01/06/2025 | M/S B.K.ENTERPRISE. | 121.96 | 0 | 0 | 100
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Acceptance cum work order for Construction of boundary wall with column structure at OHR site, PH No-2 & 3 in connection with augmentation of Padmapukuria w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/002261/2024-2025 | 1030/BD | 28/03/2025 | 26/06/2025 | JESMINE ENTERPRISE. | 28.96 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Acceptance cum work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Padmapukuria w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001363/2024-2025 | 409/BD | 06/02/2025 | 03/12/2025 | M/S RAJPATH CONSTRUCTION. | 51.15 | 0 | 0 | 96
16 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at P.H. No.-I, II III (Replacement) under Padmapukuria W/S scheme (Zone-I) under Block_ Minakhan Dist. - 24Pgs(N) under EMD, PHE Dte. [SM/13314] | Assistant Engineer |  | ORD/000026/2025-2026 | 696/EMD | 04/04/2025 | 04/05/2025 | GLACIER ENGINEERING CO. | 41.96 | 0 | 0 | 0
17 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Acceptance cum work order for Construction of boundary wall with column structure at OHR site in connection with augmentation of Padmapukuria w/s scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/002262/2024-2025 | 1029/BD | 28/03/2025 | 26/06/2025 | M/S B.K.ENTERPRISE. | 18.14 | 0 | 0 | 0
18 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Formal work order for Construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Padmapukuria water supply scheme (Zone - I), Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000153/2023-2024 | 1723/BD | 08/06/2023 | 02/06/2025 | MONDAL & CO. (BASIRHAT). | 152.66 | 126.14 | 82.63 | 99
19 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Acceptance cum work order for Protection works for protection of UPVC distribution pipe line at N/H/O Murshid Molla in connection with Augmentation of Padmapukuria w/s scheme (Zone-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000178/2024-2025 | 2097/BD | 26/07/2024 | 24/12/2024 | JESMINE ENTERPRISE. | 7.53 | 1.97 | 26.22 | 100
20 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 200 mm dia DI pipeline at different places in connection with Augmentation of Padmapukuria w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001394/2024-2025 | 260/HSD | 30/01/2025 | 09/02/2025 | ABDUL ALIM MONDAL. | 0.95 | 0 | 0 | 100
21 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in Padmapukuria mouza in connection with augmentation of Padmapukuria w/s scheme (Z-I), Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001326/2024-2025 | 170/HSD | 27/01/2025 | 06/02/2025 | ABDUL ALIM MONDAL. | 0.96 | 0 | 0 | 100
22 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Acceptance cum work order for Construction of Office cum Godown with sanitary & water supply arrangement i/c plinth protection at OHR site (Size-5.40x3.60 mtr.) for Augmentation of Padmapukuria w/s scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000544/2024-2025 | 2962/BD | 04/10/2024 | 01/02/2025 | JESMINE ENTERPRISE. | 13.54 | 0.7 | 5.2 | 60
23 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Acceptance cum work order for Construction of Office cum Godown with sanitary & water supply arrangement i/c plinth protection at OHR site (Size-5.40x3.60 mtr.) for Augmentation of Padmapukuria w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000543/2024-2025 | 2966/BD | 04/10/2024 | 01/02/2025 | BASIRHAT ANCHALICK SHARAMICK THIKADARY SAMABAY SAMITY LTD. | 13.5 | 5.22 | 38.65 | 60
24 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in Maliari mouza in connection with augmentation of Padmapukuria w/s scheme (Z-I), Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001328/2024-2025 | 172/HSD | 27/01/2025 | 06/02/2025 | ABDUL ALIM MONDAL. | 0.96 | 0 | 0 | 100
25 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 100 mm dia DI pipeline at different places in connection with Augmentation of Padmapukuria w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000112/2025-2026 | 939/HSD | 29/05/2025 | 08/06/2025 | ABDUL ALIM MONDAL. | 0.95 | 0 | 0 | 100
26 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 200 mm dia DI pipeline at different places in connection with Augmentation of Padmapukuria w/s scheme (Z-II), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001437/2024-2025 | 317/HSD | 04/02/2025 | 14/02/2025 | ABDUL ALIM MONDAL. | 0.95 | 0 | 0 | 100
27 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Acceptance cum work order for Land development at Over Head Reservoir site for Augmentation of Padmapukuria water supply scheme (Zone-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001451/2024-2025 | 93/BD | 08/01/2025 | 22/01/2025 | MONDAL & CO. (BASIRHAT). | 12.06 | 0 | 0 | 100
28 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | SM/13314 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Bairagi para in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001329/2024-2025 | 173/HSD | 27/01/2025 | 06/02/2025 | SARKAR ENTERPRISE & CO. | 0.94 | 0 | 0 | 100
Total | [13 empty] | 1553.8 | 904.58 | 58.22