## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC | SM/13350 | Augmentation | Additional Survey work for DPR Preparation for PARUI Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE | Assistant Engineer | Junior Engineer | ORD/002494/2021-2022 | 461 / BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.04 | 2.04 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC | SM/13350 | Augmentation | Route Survey,design drawing & DPR Preparation for PARUI Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002888/2021-2022 | 460/BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 100 | 1
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC | SM/13350 | Augmentation | New connection charges for Parui W/s scheme. Memo no. 1006419455/Quot/03 |  |  | VCH/003381/2022-2023 |  | 21/11/2022 | 21/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.51 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC | SM/13350 | Augmentation | New Service Connection for PH No.- under Parui W/S Scheme |  |  | BILL/00009/2022-2023 | 95/EMD | 26/11/2022 | 26/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.51 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC | SM/13350 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 1262/BD | 25/04/2023 | 25/04/2023 | Resource Division | 190.25 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC | SM/13350 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 1645/BD | 02/06/2023 | 02/06/2023 | Resource Division | 10.32 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC | SM/13350 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000144/2023-2024 | 4421/BD | 10/11/2023 | 10/11/2023 | Resource Division | 39.07 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC | SM/13350 | Augmentation | Formal work order for Laying of DI / UPVC distribution pipe line & Providing FHTC (Functional Household Tap Connection) by Augmentation for Parui (Zone - II) water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000150/2023-2024 | 1711/BD | 08/06/2023 | 26/06/2025 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 583.8 | 367.49 | 62.95 | 25
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC | SM/13350 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing FHTC (Functional Household Tap Connection) for Augmentation of Parui Zone-I water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000073/2023-2024 | 1440/BD | 11/05/2023 | 09/08/2023 | SANJIB DEY | 113.91 | 109.5 | 96.13 | 60
10 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC | SM/13350 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (rep.) under Parui W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001126/2023-2024 | 4718/EMD | 04/08/2023 | 01/09/2025 | A.S. ENTERPRISE | 39.16 | 0 | 0 | 40
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC | SM/13350 | Augmentation | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Parui W/S Scheme including increasing the height of back wash tank at Swarupnagar Block under Basirhat Sub Division, PHE Dte. capacity - 160.00 cum/hr. | Assistant Engineer | Junior Engineer | ORD/002034/2023-2024 | 925/BD | 15/03/2024 | 10/03/2025 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 37.26 | 0 | 0 | 50
Total | [13 empty] | 1027.66 | 483.87 | 47.08